## 2022-23 State Capital Program -
Project | Sector | TEI | Agency | Budget year | Est completion date | Estimated expenditure to 30.06.2022 | Estimated remaining expenditure | Fixed notes
New Wyndham Law Court Development (Werribee) | Justice and emergency services | $271m | Court Services Victoria | 2022-23 | qtr 1 2024-25 | $11m | $260m | The project's cashflow has been revised in line with a revised project schedule.
Bendigo Law Courts Redevelopment (Bendigo) | Justice and emergency services | $152m | Court Services Victoria | 2022-23 | qtr 4 2023-24 | $92m | $61m | The estimated completion date has been revised due to a revised project scope, with construction of the Bendigo Law Court expected to be complete by quarter 2 2022-23 and the Bendigo Drug Court by quarter 4 2023-24. The project's cashflow has been revised in line with a revised project schedule.
County Court Facility Project (Melbourne) | Justice and emergency services | $347m | Court Services Victoria | 2022-23 | qtr 4 2021-22 | $347m | $0m | The Victorian Government will purchase the County Court building at the end of the current lease. The leasehold is due to expire in May 2022. The building will continue to house the County Court.
Essential maintenance and compliance (statewide) | Education and Training | $120m | Department of Education and Training | 2022-23 | qtr 4 2025-26 | $0m | $120m
Land acquisition for new schools - municipalities of Cardinia, Casey, Greater Geelong, Hume, Melton, Whittlesea and Wyndham (various) | Education and Training | $237m | Department of Education and Training | 2022-23 | qtr 4 2024-25 | $0m | $237m
Special school upgrades (statewide) | Education and Training | $326m | Department of Education and Training | 2022-23 | qtr 2 2025-26 | $0m | $326m
New schools construction (statewide) | Education and Training | $527m | Department of Education and Training | 2022-23 | qtr 1 2025-26 | $0m | $527m | To open in 2024: - Aintree Secondary School (Interim Name) - Aintree Specialist School (Interim Name) - Alexander Boulevard Primary School (Interim Name) - Black Forest East Primary School (Interim Name) - Brookfield Primary School (Interim Name) - Lockerbie Central Primary School (Interim Name) - Lollypop Creek Secondary School (Interim Name) - Lollypop Creek Specialist School (Interim Name) - Merrifield South Primary School (Interim Name) - Officer Brunt Road Primary School (Interim Name) - Riverdale Secondary School (Interim Name) - Tarneit North Primary School (Interim Name) - Truganina North Primary School (Interim Name) New schools - additional stages: - Aintree Primary School - Aitken Hill Primary School - Gaayip-Yagila Primary School - Truganina North Secondary School (Interim Name)
Ready for school: Kinder for every three-year-old 2019-20 (statewide) | Education and Training | $282m | Department of Education and Training | 2022-23 | qtr 4 2023-24 | $74m | $209m | due to the Port of Melbourne lease transaction, the budget does not take into account any Port of Melbourne Corporation financial data beyond 2015-16.
School upgrades - growth for 2022 (metropolitan various) | Education and Training | $130m | Department of Education and Training | 2022-23 | qtr 2 2022-23 | $87m | $43m | The TEI has increased by $0.150 million due to a revised project scope, funded by a co-contribution from the school. This initiative was funded in the Building Works package announced in May 2020.
Relocatable Buildings Program 2020-21 (statewide) | Education and Training | $105m | Department of Education and Training | 2022-23 | qtr 4 2022-23 | $96m | $9m
Land Acquisition 2021-22 (various) | Education and Training | $302m | Department of Education and Training | 2022-23 | qtr 1 2024-25 | $103m | $198m | The TEI has increased by $25.250 million due to additional State funding relating to the purchase of the Richmond High School site from Homes Victoria.
TAFE Facilities modernisation Program 2018-19 (statewide) | Education and Training | $120m | Department of Education and Training | 2022-23 | qtr 3 2022-23 | $120m | $0m
Greater Shepparton Secondary College 2020-21 (Shepparton) | Education and Training | $123m | Department of Education and Training | 2022-23 | qtr 3 2022-23 | $123m | $0m | The TEI has increased by $4.022 million due to a revised project scope, funded by a co-contribution of $3.962 million from the school and by a co-contribution of $0.060 million from local government. This initiative was funded in the Building Works package announced in May 2020.
Land acquisition 2020-21 (statewide) | Education and Training | $147m | Department of Education and Training | 2022-23 | qtr 4 2022-23 | $147m | $1m
New schools construction 2021-22 (statewide) | Education and Training | $492m | Department of Education and Training | 2022-23 | qtr 3 2023-24 | $183m | $309m
Land acquisition 2018-19 (statewide) | Education and Training | $301m | Department of Education and Training | 2022-23 | qtr 4 2022-23 | $295m | $6m | The TEI has decreased by $19.554 million due to a return of Growth Area Infrastructure Contributions as a lower amount of funding was required.
New schools construction 2019-20 (statewide) | Education and Training | $605m | Department of Education and Training | 2022-23 | qtr 1 2022-23 | $604m | $1m | The TEI has increased by $0.509 million due to a co-contribution from McKinnon Secondary College. This is offset by a TEI decrease of $20.311 million due to the savings being redirected from this program to other school projects. The TEI has also decreased by a further $2.010 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
National Water Infrastructure Development Fund - National Partnership Agreement (regional various) | Water | $169m | Department of Environment, Land, Water and Planning | 2022-23 | qtr 4 2025-26 | $118m | $51m | The TEI has increased by $15.913 million due to additional Commonwealth Government funding. The estimated completion date has been revised to quarter 4 2025-26 to reflect a more accurate forecast.
Suburban Parks Program (Creating a Ring of New Parkland) (metropolitan) | Environment | $192m | Department of Environment, Land, Water and Planning | 2022-23 | qtr 4 2023-24 | $126m | $66m | The TEI has increased by $121.500 million due to additional funding to meet forecast capital costs for land acquisition and parkland establishment. The project's cashflow has been revised in line with a revised project schedule.
More hospital and aged care beds for Melbourne's East (Angliss Hospital Expansion Stage 2) (Upper Ferntree Gully) | Health and human services | $112m | Department of Health | 2022-23 | qtr 4 2026-27 | $0m | $112m | The TEI has increased by $8.580 million due to market conditions. The project's cashflow has been revised in line with a revised project schedule due to COVID-19 impacts.
Expanding mental health treatment facilities for Victoria's youth (statewide) | Health and human services | $141m | Department of Health | 2022-23 | qtr 4 2024-25 | $0m | $141m | The project's cashflow has been revised in line with a revised project schedule.
Additional acute mental health beds in regional Victoria (various) | Health and human services | $196m | Department of Health | 2022-23 | qtr 2 2026-27 | $0m | $196m
Emergency Departments Expansion Program - Casey Hospital and Werribee Mercy Hospital (Casey) (Werribee) | Health and human services | $236m | Department of Health | 2022-23 | qtr 4 2026-27 | $0m | $236m
Regional Health Infrastructure Fund 2022-23 (regional various) | Health and human services | $300m | Department of Health | 2022-23 | qtr 4 2025-26 | $0m | $300m
Redevelopment of Thomas Embling Hospital - Stage 2 (Fairfield) | Health and human services | $124m | Department of Health | 2022-23 | qtr 4 2024-25 | $2m | $122m | The TEI includes $11.000 million reprioritised from Expanding and improving bed-based forensic mental health services: Thomas Embling Hospital (Fairfield).
Building a world class hospital in Maryborough (Maryborough) | Health and human services | $100m | Department of Health | 2022-23 | qtr 2 2024-25 | $3m | $97m | The project's cashflow and estimated completion date have been revised in line with a revised project schedule due to COVID-19 impacts.
Warrnambool Base Hospital redevelopment (incl Warrnambool Logistics Hub) (Warrnambool) | Health and human services | $384m | Department of Health | 2022-23 | qtr 4 2025-26 | $4m | $380m | The project's cashflow has been revised in line with a revised project schedule.
Expanding and improving bed-based forensic mental health services: Thomas Embling Hospital (Fairfield) | Health and human services | $339m | Department of Health | 2022-23 | qtr 4 2024-25 | $9m | $330m | The TEI has decreased by $11.000 million due to funds being redirected to the Redevelopment of Thomas Embling Hospital - Stage 2 (Fairfield). The project's cashflow has been revised in line with a revised project schedule.
Ballarat Health Services expansion and redevelopment and the new Central Energy Plant (Ballarat) | Health and human services | $542m | Department of Health | 2022-23 | qtr 2 2028-29 | $19m | $523m | The project's cashflow and estimated completion date have been revised in line with a revised project schedule.
Regional Health Infrastructure Fund 2020-21 (regional various) | Health and human services | $120m | Department of Health | 2022-23 | qtr 4 2023-24 | $28m | $92m | The project's cashflow and estimated completion date have been revised in line with a revised project schedule due to COVID-19 impacts.
More help for Victorian mums and dads (statewide) | Health and human services | $123m | Department of Health | 2022-23 | qtr 2 2023-24 | $28m | $95m | The project's cashflow has been revised in line with a revised project schedule due to COVID-19 impacts.
COVID catch-up plan (statewide) | Health and human services | tbc | Department of Health | 2022-23 | tbc | $35m | tbc | The TEI and full cashflows will be disclosed following the outcome of commercial negotiations regarding leasing of the Frankston Private Hospital. The initiative includes $24.550 million in 2021-22 for Rapid Access Hubs. The TEI also includes $10.000 million in 2021-22 and $10.250 million in 2022-23 for the Surgical Equipment Innovation Fund and $22.232 million in 2022-23, $1.030 million in 2023-24, $1.055 million in 2024-25 and $1.082 million in 2025-26 for equipment, theatre fit-out and facility costs.
Building a bigger and better Latrobe Regional Hospital (Traralgon) | Health and human services | $217m | Department of Health | 2022-23 | qtr 4 2023-24 | $38m | $179m | The project's name has changed from Latrobe Regional Hospital redevelopment - Stage 3A (Traralgon) as published in the 2021-22 Budget. The project's cashflow has been revised in line with a revised project schedule.
Metropolitan Health Infrastructure Fund (metropolitan various) | Health and human services | $187m | Department of Health | 2022-23 | qtr 4 2023-24 | $45m | $142m | The TEI has decreased by $13.000 million due to funds being redirected to the Victorian Heart Hospital project for inclusion of a helipad. The project's cashflow has been revised in line with a revised project schedule due to COVID-19 impacts.
Regional Health Infrastructure Fund 2019-20 (regional various) | Health and human services | $100m | Department of Health | 2022-23 | qtr 4 2023-24 | $47m | $53m | The project's cashflow and estimated completion date have been revised in line with a revised project schedule due to COVID-19 impacts.
Wonthaggi Hospital emergency department expansion (Wonthaggi) | Health and human services | $115m | Department of Health | 2022-23 | qtr 4 2022-23 | $63m | $52m | The project's cashflow has been revised in line with a revised project schedule.
Ten new community hospitals to give patients the best care (statewide) | Health and human services | $675m | Department of Health | 2022-23 | qtr 4 2024-25 | $94m | $581m | The TEI includes $51.353 million from the Infrastructure Planning and Acceleration Fund. The project's cashflow has been revised in line with a revised project schedule.
Building a world class hospital for Frankston families (Frankston) | Health and human services | $1,118m | Department of Health | 2022-23 | qtr 3 2025-26 | $101m | $1,017m | The TEI component of the total project cost has increased by $512.824 million. This project is a PPP where the upfront capital investment has resulted in additional scope and whole of life benefits while remaining within the project's affordability benchmark. The estimated completion date has been revised to 2025-26 to reflect the completion date of the new hospital tower by the end of 2025, with the redevelopment operational in early 2026 and remaining refurbishment and other works completed by 2027-28.
Meeting ambulance response Times (statewide) | Health and human services | $169m | Department of Health | 2022-23 | qtr 4 2022-23 | $127m | $42m | The project's cashflow has been revised in line with a revised project schedule due to COVID-19 impacts.
Northern Hospital inpatient expansion - Stage 2 (Epping) | Health and human services | $163m | Department of Health | 2022-23 | qtr 2 2022-23 | $156m | $6m | The project's cashflow has been revised in line with a revised project schedule due to COVID-19 impacts.
A pathway to more acute mental health beds: Responding to the Royal Commission into the Victoria's Mental Health System interim report (statewide) | Health and human services | $492m | Department of Health | 2022-23 | qtr 3 2023-24 | $173m | $319m | The project's cashflow has been revised in line with a revised project schedule.
Goulburn Valley Health redevelopment - planning and development (Shepparton) | Health and human services | $229m | Department of Health | 2022-23 | qtr 4 2022-23 | $206m | $24m | The project's cashflow has been revised in line with a revised project schedule.
Regional Health Infrastructure Fund (regional various) | Health and human services | $250m | Department of Health | 2022-23 | qtr 4 2023-24 | $224m | $26m | The project's name has changed from Regional Health Infrastructure Fund 2018-19 (regional various) published in the 2021-22 Budget. The project's cashflow and estimated completion date have been revised in line with a revised project schedule due to COVID-19 impacts.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Health and human services | $318m | Department of Health | 2022-23 | qtr 4 2021-22 | $310m | $8m | The TEI has increased by $11.100 million due to scope increases and market conditions. The project's cashflow has been revised in line with a revised project due to COVID-19 impacts.
Victorian Heart Hospital (Clayton) | Health and human services | $577m | Department of Health | 2022-23 | qtr 2 2023-24 | $474m | $103m | The TEI has increased by $13.000 million with funding sourced from the Metropolitan Health Infrastructure Fund for the inclusion of a helipad. The project's cashflow has been revised in line with a revised project schedule.
Building a better hospital for Melbourne's inner west (Footscray) | Health and human services | $1,999m | Department of Health | 2022-23 | qtr 1 2025-26 | $503m | $1,496m | The TEI component of the total project cost has increased by $503.605 million. This project is a PPP where the upfront capital investment has resulted in additional scope and whole of life benefits while remaining within the project's affordability benchmark. The increased TEI also reflects the inclusion of the Victoria University project components which are to be reimbursed by Victoria University. The project's cashflow has been revised in line with the contracted project schedule.
Modernisation of metropolitan Melbourne Public Sector Residential Aged Care Services Strategy: Stage 3 Kingston Project (Cheltenham) | Health and human services | $135m | Department of Health | 2022-23 | qtr 4 2025-26 | tbc | tbc | The project's cashflow will be disclosed following further project planning and development.
Barwon Women's and Children's Hospital (Geelong) | Health and human services | $500m-$525m | Department of Health | 2022-23 | tbc | tbc | tbc | The TEI and estimated completion date will be disclosed following further project development and procurement processes. The TEI includes $50.000 million of Commonwealth Government funding under the Community Health and Hospitals Program agreement.
New Melton Hospital (Cobblebank) | Health and human services | $900m-$1,000m | Department of Health | 2022-23 | tbc | tbc | tbc | The TEI and estimated completion date will be disclosed following further project planning and development. Planning and detailed design is expected to be completed by 2024-25 with construction expected to take over 4 years.
Geelong City Deal (Geelong) | Culture, sport and community | $414m | Department of Jobs, Precincts and Regions | 2022-23 | qtr 4 2025-26 | $0m | $414m | The TEI has increased by $121.735 million due to additional funding to meet forecast capital costs to deliver the Geelong Convention and Exhibition Centre. The TEI includes Commonwealth Government funding.
Melbourne Arts Precinct transformation Phase One (Melbourne) | Culture, sport and community | $1,572m | Department of Jobs, Precincts and Regions | 2022-23 | tbc | $23m | $1,549m | The TEI has increased by $162.241 million due to expanded scope of works including the renewal of the State Theatre and Public Realm and associated works. The estimated completion date will be disclosed following further project planning and development.
Technology and resources to support Victoria's fines system (statewide) | Justice and emergency services | $142m | Department of Justice and Community Safety | 2022-23 | qtr 4 2024-25 | $41m | $101m | The prior reporting of this initiative was 'tbc' and is now disclosed following contract award.
Emergency services high-priority infrastructure (statewide) | Justice and emergency services | $126m | Department of Justice and Community Safety | 2022-23 | qtr 4 2024-25 | $55m | $70m | The TEI has increased by $4.661 million to include new funding and deliverables announced in the 2021-22 Budget for the Emergency Service Organisations Infrastructure initiative (statewide). The project's cashflow and estimated completion date have been revised in line with a revised project schedule.
Women's prison system capacity (statewide) | Justice and emergency services | $189m | Department of Justice and Community Safety | 2022-23 | qtr 2 2022-23 | $81m | $107m | The project's cashflow has been revised in line with a revised project schedule.
Men's prison system capacity (statewde) | Justice and emergency services | $796m | Department of Justice and Community Safety | 2022-23 | qtr 2 2023-24 | $239m | $557m | The TEI has decreased by $8.990 million due to a revised project scope. The project's cashflow and estimated completion date have been revised in line with a revised project schedule due to COVID-19 impacts.
Community Safety Statement (statewide) | Justice and emergency services | $315m | Department of Justice and Community Safety | 2022-23 | various | $303m | $13m
New youth justice facility (metropolitan) | Justice and emergency services | $420m | Department of Justice and Community Safety | 2022-23 | qtr 1 2022-23 | $388m | $32m | The project's cashflow has been revised in line with a revised project schedule.
Western Plains Correctional Centre (Lara) | Justice and emergency services | $1,119m | Department of Justice and Community Safety | 2022-23 | qtr 2 2022-23 | $999m | $119m | The project name has changed from the Chisholm Road prison project that was published in the 2021-22 Budget. The project's cashflow has been revised in line with a revised project schedule.
Metropolitan road upgrades (metropolitan) | Transport | $101m | Department of Transport | 2022-23 | qtr 4 2025-26 | $0m | $101m | The TEI includes $6.700 million of funding from Wyndham City Council.
Maintaining Victoria's road network (statewide) | Transport | $119m | Department of Transport | 2022-23 | qtr 4 2022-23 | $0m | $119m
Mickleham Road Upgrade - Stage 1 (Greenvale) | Transport | $207m | Department of Transport | 2022-23 | qtr 4 2025-26 | $0m | $207m | The TEI excludes $14.851 million for early works announced in the 2021-22 Budget. The TEI includes $109.540 million of Commonwealth Government funding.
Metropolitan Network Modernisation Program (metropolitan various) | Transport | $1,348m | Department of Transport | 2022-23 | qtr 2 2022-23 | $1,304m | $44m | The TEI has decreased by $43.765 million due to program savings. These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future-proofing works, that are being delivered jointly with the Level Crossing Removal Program.
Metropolitan road and intersection upgrades (metropolitan various) | Transport | $117m | Department of Transport | 2022-23 | qtr 4 2023-24 | $2m | $115m
85 by 2025 (Level Crossing Removal) (metropolitan various) | Transport | $8,946m | Department of Transport | 2022-23 | qtr 2 2025-26 | $3,142m | $5,804m | This initiative was previously listed as 75 by 2025 (Level Crossing Removal). The TEI has increased by $2 536 million to include an additional 10 level crossing removals announced in the 2021-22 Budget Update, and decreased by $140.000 million due to program savings.
Improving the Calder Freeway (Calder Park) | Transport | $100m | Department of Transport | 2022-23 | tbc | $3m | $97m | The TEI includes $50.000 million of Commonwealth Government funding. The estimated completion date will be determined as planning on the project progresses.
West Gate Tunnel (metropolitan various) | Transport | $10,212m | Department of Transport | 2022-23 | qtr 2 2025-26 | $5,834m | $4,378m | The TEI has increased by $3.924 billion to reflect the settlement agreed between the State, Transurban and the Design and Construct contractor in December 2021 and excludes $56.47 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The project is now expected to be completed by late 2025.
Level Crossing Removal Program (metropolitan various) | Transport | $6,343m | Department of Transport | 2022-23 | qtr 2 2022-23 | $6,125m | $218m | The TEI has decreased by $216.235 million due to program savings. The TEI includes $151.000 million of Commonwealth Government funding for the Main Road, St Albans project, and excludes $319.868 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Delivering the Road Safety Action Plan (statewide) | Transport | $246m | Department of Transport | 2022-23 | qtr 4 2024-25 | $29m | $216m | The TEI includes $142.484 million of Commonwealth Government funding and a further $103.067 million of funding from the Transport Accident Commission.
Targeted Road Safety Works (statewide) | Transport | $106m | Department of Transport | 2022-23 | qtr 2 2022-23 | $34m | $72m | The TEI includes $78.242 million of Commonwealth Government funding and funding from the Transport Accident Commission.
Hall Road Upgrade (Skye) | Transport | $283m | Department of Transport | 2022-23 | qtr 1 2024-25 | $37m | $246m | The TEI includes $141.252 million of Commonwealth Government funding.
Western Port Highway (Skye) | Transport | $114m | Department of Transport | 2022-23 | qtr 2 2022-23 | $42m | $71m | The TEI includes $57.500 million of Commonwealth Government funding.
Great Ocean Road Renewal (Barwon South West) | Transport | $255m | Department of Transport | 2022-23 | qtr 4 2024-25 | $43m | $212m
Road Safety Strategy (statewide) | Transport | $320m | Department of Transport | 2022-23 | qtr 4 2024-25 | $46m | $274m | The TEI has decreased by $9.907 million due to project scope changes. The TEI includes $183.300 million of Commonwealth Government funding and funding from the Transport Accident Commission.
Road maintenance blitz (statewide) | Transport | $109m | Department of Transport | 2022-23 | qtr 4 2022-23 | $73m | $36m
Pavement Maintenance and Renewal Program (statewide) | Transport | $102m | Department of Transport | 2022-23 | qtr 4 2022-23 | $82m | $20m | The TEI has decreased by $4.050 million due to savings. The estimated practical completion date has been revised to quarter 4 2021-22 due to delivery issues including ground access and detailed design complications.
Rural and Regional Roads Package - Improving the South Gippsland Highway (Gippsland region) | Transport | $109m | Department of Transport | 2022-23 | qtr 4 2023-24 | $94m | $15m | The TEI has decreased by $1.670 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards, and includes $57.506 million of Commonwealth Government funding.
Princes Highway East Duplication Stage 3 (regional various) | Transport | $245m | Department of Transport | 2022-23 | qtr 4 2023-24 | $98m | $148m | The TEI excludes by $7.841 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Keeping Victorians Moving (metropolitan) | Transport | $173m | Department of Transport | 2022-23 | qtr 4 2023-24 | $101m | $72m | The TEI has reduced by $1.502 million due to savings.
Rural and Regional Roads Package - Echuca-Moama bridge (Echuca) | Transport | $165m | Department of Transport | 2022-23 | qtr 4 2023-24 | $142m | $23m | The TEI includes $76.376 million of Commonwealth Government funding for the Victorian portion. The TEI excludes funding contributions from the New South Wales Government and the Commonwealth Government portion for New South Wales. The TEI has decreased by $7.787 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Barwon Heads Road Upgrade (Barwon Heads) | Transport | $365m | Department of Transport | 2022-23 | qtr 2 2023-24 | $143m | $222m | The TEI includes $292.000 million of Commonwealth Government funding. The estimated completion date has been brought forward to quarter 2 2023-24 due to early contract award.
Urban Congestion Package - O'Herns Road upgrade (Epping) | Transport | $149m | Department of Transport | 2022-23 | qtr 1 2023-24 | $147m | $2m | The TEI has increased by $35.499 million due to utility relocation and COVID-19 impacts, and includes $50.000 million of Commonwealth Government funding.
Metropolitan and regional restoration and maintenance (statewide) | Transport | $195m | Department of Transport | 2022-23 | qtr 4 2022-23 | $186m | $9m | The estimated completion date has been revised to quarter 4 2022-23 due to ground access and detailed design processes impacting project timeframes.
TAC Victoria's Road Safety Strategy, Towards Zero 2016-2020 (TZ2) (regional various) | Transport | $237m | Department of Transport | 2022-23 | qtr 2 2022-23 | $196m | $41m
M80 Ring Road upgrade (north and west metropolitan region) | Transport | $657m | Department of Transport | 2022-23 | qtr 3 2022-23 | $406m | $251m | The TEI includes $349.130 million of Commonwealth Government funding, and excludes $16.273 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The estimated completion date relates to the Sydney Road to Edgars Road section, with further planning works still being undertaken for additional sections.
Mordialloc Freeway (Braeside) | Transport | $520m | Department of Transport | 2022-23 | qtr 2 2023-24 | $489m | $31m | The TEI has decreased by $2.350 million due to savings, and excludes $1.000 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Western Highway duplication - Ballarat to Stawell (regional various) | Transport | $656m | Department of Transport | 2022-23 | tbc | $591m | $66m | The TEI includes $499.380 million of Commonwealth Government funding. The estimated completion date is to be confirmed due to legal challenges.
Road Safety Strategy 2013-2022 (statewide) | Transport | $628m | Department of Transport | 2022-23 | qtr 2 2022-23 | $608m | $20m | The TEI has decreased by $1.700 million due to reprioritisation towards the Targeted Road Safety Works project. This initiative is funded by the Transport Accident Commission.
Suburban Roads Upgrade - Northern Roads Upgrade and South Eastern Roads Upgrade (statewide) | Transport | $2,513m | Department of Transport | 2022-23 | qtr 2 2025-26 | $747m | $1,766m | The TEI has increased by $303.857 million due to market conditions and excludes $59.858 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The TEI includes $1 140.000 million of Commonwealth Government funding.
Monash Freeway upgrade - Stage 2 (South-East Melbourne) | Transport | $1,019m | Department of Transport | 2022-23 | qtr 2 2022-23 | $785m | $234m | The TEI includes $686.216 million of Commonwealth Government funding. The TEI excludes $34.523 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
North East Link (State and Freeway Packages) (Greensborough) | Transport | tbc | Department of Transport | 2022-23 | qtr 2 2028-29 | tbc | tbc | North East Link is supported by $15.400 billion of asset funding and is being delivered through a series of works packages. The TEI and estimated completion dates will be reported as procurement processes and commercial arrangements are finalised.
Arden Precinct redevelopment (metropolitan) | Transport | tbc | Department of Transport | 2022-23 | tbc | tbc | tbc | The TEI and estimated completion date for this initiative are not disclosed at this time to ensure negotiations with affected landholders are not prejudiced.
Acquisition of Bendigo GovHub (Bendigo) | Culture, sport and community | $121m | Department of Treasury and Finance | 2022-23 | qtr 2 2022-23 | $0m | $121m | The estimated completion date has been revised to quarter 2 2022-23 in line with a revised project schedule.
Homes Victoria Ground Lease Model Project 2 (metropolitan) | Health and human services | $260m | Director of Housing | 2022-23 | tbc | $5m | $255m | The TEI includes project development, market testing, procurement costs and the Government's capital contribution to the project. It is expected that the Government investment will be matched by an equivalent contribution by the private sector for the Build to Rent element of the project, being an integral part of the delivery model. The TEI excludes the service payment to be made by Homes Victoria to Project Co during the Operational Phase.
Big Housing Build physical improvements (statewide) | Health and human services | $184m | Director of Housing | 2022-23 | qtr 4 2026-27 | $20m | $164m
Public housing renewal program (statewide) | Health and human services | $185m | Director of Housing | 2022-23 | qtr 2 2024-25 | $53m | $132m
Homes Victoria Ground Lease Model Project 1 (metropolitan) | Health and human services | $264m | Director of Housing | 2022-23 | qtr 3 2023-24 | $114m | $149m | The TEI includes a capital contribution, State costs, development costs covered by the Service Payment exclusive of GST and retained risk during the delivery phase. The capital expenditure is higher than the reported TEI due to an offset from rental income.
Building works stimulus (statewide) | Health and human services | $155m | Director of Housing | 2022-23 | qtr 4 2022-23 | $153m | $2m
Big Housing Build (statewide) | Health and human services | $3,067m | Director of Housing | 2022-23 | qtr 4 2026-27 | $965m | $2,102m | The TEI has been updated from the Big Housing Build program announced in the 2020-21 Budget to include the Building New Homes to Fight Homelessness program and to reflect a reclassification of certain expenditure between capital and operating in line with accounting standards.
FRV Capital Upgrades Program (statewide) | Justice and emergency services | $104m | Fire Rescue Victoria | 2022-23 | qtr 4 2025-26 | $11m | $93m | This program includes 17 projects previously published separately in the 2021-22 Budget. These projects will be managed as a single capital upgrades program by the Community Safety Building Authority. The TEI has decreased by $11.026 million due to a revised program scope. The estimated completion date has been revised to quarter 4 2025-26 to reflect a revised schedule of works. The estimated completion date applies to the total program of works. Individual projects may be completed ahead of this date. The location and previous project names published in the 2021-22 Budget were: Armstrong Creek Fire Station - construction (Armstrong Creek); Baker St Temp Station (Richmond); Ballarat City Fire Station - construction (Ballarat City); Bendigo Fire Station - construction (Bendigo); Boronia Fire Station - construction (Boronia); Box Hill Fire Station - construction (Box Hill); Broadmeadows Fire Station Refurbishment (Broadmeadows); Clyde North Fire Station - construction (Clyde North); Corio Fire Station - construction (Corio); Craigieburn Fire Station - construction (Craigieburn); Frankston Fire Station - construction (Frankston); Lara Fire Station - construction (Lara); Latrobe West Fire Station - construction (Latrobe West); Mornington Fire Station - construction (Mornington); Port Melbourne Fire Station - construction (Port Melbourne); Ringwood Fire Station Refurbishment (Ringwood); and Springvale Fire Station - construction (Springvale).
Connections project (regional various) | Water | $1,076m | Goulburn-Murray Rural Water Corporation | 2022-23 | qtr 2 2021-22 | $1,076m | $0m
Water efficiency project (regional various) | Water | $123m | Goulburn-Murray Rural Water Corporation | 2022-23 | ongoing | $30m | $93m | The TEI has decreased due to the Connections project which was previously included in completed projects.
Kardinia Park Stadium Stage 5 redevelopment (Geelong) | Culture, sport and community | $141m | Other public non-financial corporations | 2022-23 | qtr 4 2022-23 | $10m | $131m
Building a world-class Geelong Performing Arts Centre (Geelong) | Culture, sport and community | $140m | Other public non-financial corporations | 2022-23 | qtr 2 2023-24 | $33m | $107m
State Basketball Centre redevelopment (Knox) | Culture, sport and community | $128m | Other public non-financial corporations | 2022-23 | qtr 1 2023-24 | $54m | $75m | The TEI has decreased by $3.551 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The TEI includes a $27.000 million contribution from Knox City Council.
Melbourne Park redevelopment stage three (Melbourne) | Culture, sport and community | $296m | Other public non-financial corporations | 2022-23 | qtr 1 2022-23 | $296m | $0m | The TEI includes $20.500 million from Melbourne Olympic Parks Trust and $3.972 million from Tennis Australia. The project is expected to reach practical completion in quarter 4 2021-22, with financial completion expected to be quarter 1 2022-23.
North East Link - Primary Package (Tunnels) and State Toll Co | Transport | $14,034m | State Toll Co | 2022-23 | qtr 2 2028-29 | $1,104m | $12,930m | The TEI includes the $11.100 billion contract with the Spark consortium to deliver the Primary Package and other costs associated with the operations of STC. The TEI includes $1.750 billion of Commonwealth Government funding. The TEI excludes financing costs associated with the Primary Package. The State Tolling Corporation is responsible for providing funding contributions to the North East Link - Primary Package (Tunnels).
Train radio system upgrade (metropolitan) | Transport | $173m | Victorian Rail Track | 2022-23 | qtr 4 2027-28 | $0m | $173m | The TEI includes $31.000 million and $11.370 million of funding from the Digital Train Radio System (DTRS) project and Metropolitan rail infrastructure renewal program respectively.
More VLocity trains (regional) | Transport | $250m | Victorian Rail Track | 2022-23 | qtr 4 2026-27 | $0m | $250m
Tram infrastructure upgrades (metropolitan various) | Transport | $368m | Victorian Rail Track | 2022-23 | qtr 4 2025-26 | $0m | $368m | This initiative supports the Next Generation Trams initiative by delivering a Train Maintenance Facility at Maidstone, upgrades to the Southbank tram depot and substation upgrades across the network. The total value of the Next Generation Trams project is $1.85 billion.
Geelong Fast Rail (regional various) | Transport | tbc | Victorian Rail Track | 2022-23 | tbc | $0m | tbc | The State and Commonwealth governments have committed $2.000 billion each to the project. The TEI and estimated completion date will be disclosed following finalisation of the business case and project procurement. The estimated expenditure excludes $60.000 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
High Capacity Metro Trains (metropolitan various) | Transport | $2,248m | Victorian Rail Track | 2022-23 | qtr 1 2023-24 | $1,751m | $498m | The TEI has increased by $5.000 million due to project scope changes. The TEI includes financing costs.
Regional Rail Sustainability (regional) | Transport | $205m | Victorian Rail Track | 2022-23 | qtr 4 2025-26 | $1m | $204m
Regional Rail Revival - Warrnambool Line Upgrade - Stage 2 (regional various) | Transport | $260m | Victorian Rail Track | 2022-23 | qtr 1 2024-25 | $5m | $255m | The TEI includes $208.000 million of Commonwealth Government funding.
Metro Tunnel (metropolitan various) | Transport | $12,361m | Victorian Rail Track | 2022-23 | qtr 2 2025-26 | $8,678m | $3,683m | The TEI has increased by $106.238 million due to COVID-19 related payments, and excludes $182.856 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The TEI excludes financing costs.
Rolling stock maintenance and disposal programs (statewide) | Transport | $125m | Victorian Rail Track | 2022-23 | qtr 1 2025-26 | $11m | $114m
Regional Rail Revival - Shepparton Line Upgrade - Stage 3 (Shepparton) | Transport | $400m | Victorian Rail Track | 2022-23 | qtr 4 2023-24 | $19m | $381m | The TEI includes $320.000 million of Commonwealth Government funding.
Caulfield Rationalisation Works (metropolitan various) | Transport | $240m | Victorian Rail Track | 2022-23 | qtr 4 2025-26 | $20m | $221m
Regional Rail Revival - Waurn Ponds Track Duplication - Stage 2 (regional various) | Transport | $899m | Victorian Rail Track | 2022-23 | qtr 2 2024-25 | $24m | $875m | The TEI includes $754.000 million of Commonwealth Government funding.
New Trams (metropolitan various) | Transport | $110m | Victorian Rail Track | 2022-23 | qtr 4 2023-24 | $76m | $34m
Regional Rail Revival - Bendigo/Echuca Line Upgrade (regional various) | Transport | $175m | Victorian Rail Track | 2022-23 | qtr 2 2022-23 | $88m | $87m | The TEI includes $158.680 million of Commonwealth Government funding, and excludes $0.368 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Regional rail sustainability (statewide) | Transport | $465m | Victorian Rail Track | 2022-23 | qtr 4 2024-25 | $94m | $370m
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | Transport | $469m | Victorian Rail Track | 2022-23 | qtr 2 2023-24 | $99m | $370m | The TEI has increased by $317.199 million due to project scope changes and market conditions. The reporting for the project was previously 'tbc' and has been confirmed following contract award.
New metropolitan trains (statewide) | Transport | $986m | Victorian Rail Track | 2022-23 | qtr 2 2026-27 | $102m | $884m | The reporting for the project was previously 'tbc' and has now been disclosed.
Dandenong Corridor Readiness Works (metropolitan various) | Transport | $277m | Victorian Rail Track | 2022-23 | qtr 2 2025-26 | $140m | $137m
Regional Rail Revival - Shepparton Corridor Upgrade - Stage 2 (Shepparton) | Transport | $314m | Victorian Rail Track | 2022-23 | qtr 2 2022-23 | $169m | $145m | The TEI excludes $1.103 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Regional Rail Revival - Gippsland Line Upgrade Stage 1 (regional various) | Transport | $531m | Victorian Rail Track | 2022-23 | qtr 2 2022-23 | $169m | $363m | The TEI includes $447.700 million of Commonwealth Government funding, and excludes $1.436 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Next Generation Trams (metropolitan various) | Transport | $1,468m | Victorian Rail Track | 2022-23 | qtr 4 2028-29 | $172m | $1,296m | The TEI has decreased by $15.000 million due to movement of scope to the Delivering the Tram Plan initiative.
Melbourne Airport Rail (metropolitan various) | Transport | tbc | Victorian Rail Track | 2022-23 | tbc | $201m | tbc | The State and Commonwealth governments have committed $5.000 billion each to the project. The TEI and estimated completion date are not reported at this time as procurement processes and commercial arrangements are still to be finalised. The estimated expenditure excludes $180.839 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
More regional trains - Regional Network Development Plan (regional various) | Transport | $224m | Victorian Rail Track | 2022-23 | qtr 4 2022-23 | $204m | $20m | The estimated completion date has been revised to quarter 4 2022-23 due to COVID-19 impacts.
New VLocity carriages for the regional network (regional various) | Transport | $251m | Victorian Rail Track | 2022-23 | qtr 2 2022-23 | $209m | $42m | The estimated completion date has been revised to quarter 2 2022-23 to align with completion of stabling and maintenance works for the Warrnambool and Geelong Line.
Regional Rail Revival - Warrnambool and Geelong Line Upgrade (regional various) | Transport | $250m | Victorian Rail Track | 2022-23 | qtr 2 2022-23 | $214m | $36m | The TEI includes $226.345 million of Commonwealth Government funding, and excludes $1.611 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The estimated completion date has been revised to reflect a revised project schedule.
Additional VLocity trains (regional various) | Transport | $340m | Victorian Rail Track | 2022-23 | qtr 4 2023-24 | $218m | $122m
Frankston Line stabling (Kananook) | Transport | $257m | Victorian Rail Track | 2022-23 | qtr 4 2025-26 | $238m | $19m | The TEI has increased by $17.300 million due to increased land acquisition and land contamination rectification costs.
Car Parks for Commuters (statewide) | Transport | $618m | Victorian Rail Track | 2022-23 | qtr 2 2024-25 | $280m | $338m | The TEI has increased by $132.899 million due to additional Commonwealth Government funding for the delivery of car parks and related infrastructure. The TEI excludes $0.397 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Hurstbridge Line Upgrade Stage 2 (metropolitan various) | Transport | $603m | Victorian Rail Track | 2022-23 | qtr 3 2022-23 | $311m | $292m | The TEI has increased by $66.000 million and the estimated completion date has been revised due to the identification of the Eltham Copper Butterfly and associated habitat requiring a scope change and impacting the project's completion schedule. The TEI excludes $0.014 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Murray Basin Rail Project (regional various) | Transport | $794m | Victorian Rail Track | 2022-23 | tbc | $417m | $378m | The TEI includes $470.400 million of Commonwealth Government funding, and excludes $17.286 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The completion date will be disclosed following completion of the procurement process.
E-Class Tram Infrastructure Program (metropolitan various) | Transport | $741m | Victorian Rail Track | 2022-23 | qtr 4 2025-26 | $461m | $280m | The TEI has increased by $6.000 million due to reprioritisations from other Rolling Stock projects for safety and accessibility works to E-Class trams.
Metropolitan rail infrastructure renewal program (metropolitan various) | Transport | $1,576m | Victorian Rail Track | 2022-23 | qtr 4 2025-26 | $479m | $1,097m | As a rolling program of works, the TEI varies from year to year. The TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2018-19 to 2025-26.
Suburban Rail Loop Initial and Early Works (metropolitan various) | Transport | $2,360m | Victorian Rail Track | 2022-23 | qtr 4 2024-25 | $493m | $1,866m | The TEI excludes $90.295 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Cranbourne Line Duplication (metropolitan various) | Transport | $682m | Victorian Rail Track | 2022-23 | qtr 3 2023-24 | $623m | $59m | The TEI has decreased by $83.300 million due to savings made in project delivery. The project completion date has been brought forward due to the project being completed ahead of schedule.
New trains for Sunbury (metropolitan various) | Transport | $1,973m | Victorian Rail Track | 2022-23 | qtr 2 2024-25 | $750m | $1,223m
South Dynon train maintenance facility (statewide) | Transport | tbc | Victorian Rail Track | 2022-23 | qtr 1 2023-24 | tbc | tbc | The TEI will be disclosed following the completion of the procurement process.
Suburban Rail Loop East - Main Works | Transport | tbc | Victorian Rail Track | 2022-23 | tbc | tbc | tbc | The Suburban Rail Loop East is expected to cost between $30-34.500 billion and is targeting delivery by 2035.
Public Transport Ticketing Asset Renewal (statewide) | Transport | tbc | Victorian Rail Track | 2022-23 | tbc | tbc | tbc | The TEI and estimated completion date for this initiative are not disclosed at this time due to the commercial sensitivity of the procurement process.