## Home
Offsite Construction Project Evaluation Tool
A tool for assessing the suitability of offsite construction for Victorian infrastructure projects
About the tool
This tool is designed for project and program managers and strategic planners who are at the initial planning stages (pre-business case or business case) and want to assess which construction method would best suit the project. The tool helps identify whether the project and its elements are more suited to modular construction, volumetric pre-fabrication, non-volumetric prefabrication or traditional construction.
Usage | This tool requires information about the high-level scope of your project/program. The questions were designed to be answered without having detailed designed or construction information at hand, given that the decision of utilising offsite construction should be taken before the start of the design phase. Completing the questions should take about 10 minutes. Upon completing the tool, you will receive a report that states whether your project is applicable for offsite construction and if so to what extent.
Assistance | If anything seems to break, please try to refresh the tool (remember to save first!) and if problems persist, please get in touch. If you need additional assistance or have feedback on the tool, please contact us via email:
enquiries@opv.vic.gov.au
START >>
The Office of Projects Victoria respectfully acknowledges the Traditional Owners of the land and pays respects to their Elders, past, present, and emerging. We acknowledge and uphold their continuing relationship to this land and the lands that your assessment is being conducted in.

## Project Information
|  |  |  | ) | Previous Valid | TRUE
1. | Project Information
# | Question | Response | Additional Information |  |  |  | Validation
Q1 | Is the project similar to others previously delivered? |  | Repeated projects provide opportunity for savings in design reuse, component reuse and knowledge sharing |  |  |  | FALSE
Q2 | Is the project part of a larger program of works? |  | Programs of works across multiple sites provide opportunity for design reuse, bulk ordering of parts and program compression |  |  |  | FALSE
Q3 | Is there existing design and IP available for reuse? | [5 empty] | FALSE
Q4 | Is the project unique in terms of architectural design? |  | Projects with uniquely designed architectural elements may be better suited to traditional construction methods |  |  |  | FALSE
Q5 | Does project handover need to happen urgently after initiation? |  | OSC allows for program fast-tracking through quicker construction time |  |  |  | FALSE
Q6 | Does the project have requirements for increasing diversity? |  | The manufacturing environment of OSC has been shown to increase workforce diversity |  |  |  | FALSE
[6 empty] | Overall | FALSE
Please complete all mandatory questions
| << PREVIOUS |  | #N/A

## Project Factors
|  |  |  | Previous Valid | FALSE
2 | Project Factors | Please complete the previous section prior to filling out this section
# | Question | Response | Additional Information |  |  | Validation
Q1 | Is design repeatable or standardised? |  | Repeated or standardised design elements such as classrooms, bridge beams or housing modules. |  |  | FALSE
Q2 | Is the project likely to require significant design changes during delivery? |  | OSC requires lock-in of design early in the project lifecycle |  |  | FALSE
Q3 | Is it important to reduce design complexity? |  |  |  |  | FALSE
Q4 | Is it important to reduce site complexity? |  | OSC reduces number of trades onsite |  |  | FALSE
Q5 | Is construction constrained by external factors (e.g. occupation, school holidays)? |  | Constraint on construction requires a tight turnaround onsite, reducing onsite complexity to meet program |  |  | FALSE
Q6 | Location remote from labour and infrastructure? |  | Geographically remote sites may not have access to multiple trades in a supply chain |  |  | FALSE
Q7 | Are site conditions uncertain? (e.g. geotechnical, contamination) |  | Sites with unknown existing conditions may require design changes to accommodate for contamination, subsurface utilities etc. |  |  | FALSE
Q8 | Is your project suseptible to construction delays due to weather? |  | Projects with susceptibility to delays due to weather may be better suited to manufacture of components offsite |  |  | FALSE
Q9 | Is there an appetite to take up innovation? |  |  |  |  | FALSE
| << PREVIOUS | Please complete all madatory questions | #N/A |  | Overall | FALSE

## Construction Factors
|  |  |  | Previous Valid | FALSE
3. | Construction Factors | Please complete the previous section prior to filling out this section
# | Question | Response | Additional Information |  |  | Validation
Q1 | How difficult is the access to the construction site for this element (e.g. transport, swept path area)? |  | OSC can improve inventory management (just in time), decrease stage space requirements, and avoid double handling by allowing direct installation from the delivery vehicle. |  |  | FALSE
Q2 | How contained and/or constrained is the space/laydown area for the construction of this element? |  | Underground activities and small sites in dense urban environments usually have a contained/constrained space and limits offsite construction. |  |  | FALSE
Q3 | How significant are health & safety risks in the construction of this element? |  | Health and safety risks, such as falling from heights and working alongside live operations, can be drastically reduced by manufacturing offsite in a controlled environment where work can be automated and optimised. |  |  | FALSE
Q4 | How constrained are labour resources for this element? |  | Labour resources may be constrained for roles that require high skills and experience. OSC allows people who are presently underrepresented in traditional construction to enter the workforce. |  |  | FALSE
Q5 | How important for the project is reduction of construction waste? |  | Environmental impacts are typically reduced as materials usage and movements are optimised. OSC typically increases energy efficiency and can reduce waste by up to 90 per cent (depending on project, materials and level of automation). |  |  | FALSE
Q6 | How important for the project is reduction of onsite traffic and distruption? |  | Fewer deliveries to the site of materials and components and an accelerated timeline with OSC mean less noise, disturbance, and pollution in the surrounding area. |  |  | FALSE
[5 empty] | Overall | FALSE
| << PREVIOUS | Please complete all mandatory questions | #N/A

## Element Design
|  |  |  | Previous Valid | FALSE
4. | Element Design | Please complete the previous section prior to filling out this section
For your project, consider some elements that would typically be required that would be repeated
Project Element
| List up to three repeatable items (separated by a comma) |  | This may include: Hospitals: Bathroom modules, surgical wards, cafeteria Transport: Bridge abutments, road barriers, gantries Schools: Classrooms, roof trusses, staircases Justice: Offices, prision cells, ambulance depot Housing: Wall panels, elevators, kitchens |  |  |  | 0
# | Question | Response | Additional Information |  |  | Validation
Q1a | How complex is the design of this element? |  | Repeated projects provide opportunity for savings in design reuse, component reuse and knowledge sharing |  |  | FALSE
Q2a | How likely are significant design changes to occur during the construction phase of this element? |  | Programs of works across multiple sites provide opportunity for design reuse, bulk ordering of parts and program compression |  |  | FALSE
Q3a | How high is the level of design standardisation and/or repeatability of this element across the project/program? |  | Repeated or standardised design elements such as road barriers, toilet blocks or standard-sized classrooms |  |  | FALSE
Q4a | How easily can this element be reused for or from other projects via Digital Models, BIM or Digital Twins? |  | Projects with uniquely designed architectural elements may be better suited to traditional construction methods |  |  | FALSE
Q5a | How important is precision during construction to ensure high quality for this element? |  | Requirements for elevated levels of quality control or minimal defects, or specialised functionality such as earthquake, fire or blast resistant buildings lend the development more towards OSC. |  |  | FALSE
[5 empty] | Step 1 | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
[5 empty] | Step 2 | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
[5 empty] | Step 3 | FALSE
[5 empty] | Overall | #N/A

## Report
|  |  | Previous Valid | #N/A
#VALUE!
| #N/A | Result
Overall Project | #N/A
#N/A
Recommended OSC type | #N/A
Other OSC options | #N/A
|  | Result | LUKey |  | Display
Project Elements
FALSE
FALSE
FALSE

## Report Backend (hidden)
Construction Type | Overall Project |  | Recommended OSC Type | Other OSC Options
Traditional | From the information provided in the Tool, this project is not suited for the application of Offsite Construction. | Based on your project requirements, traditional construction may be better suited for the majority of the project. If it is still desired, more time spent upfront during design phase and possible increase in budget may allow for OSC. | Offsite construction is recommended for projects with high degrees of repeatability (either the project itself or parts of the build) where there is low uncertainty of the design during construction. | Should the project still decide to utilise OSC, the following options are available: Non-volumetric: Offsite preassembly of components that have no usable space by themselves. These preassemblies may be structural or non-structural and include open and closed planar or panelised systems e.g., cladding panels, precast concrete sections: posts, beams, slabs and columns, and structural steelwork trusses. Volumetric: Offsite preassembly of components that create usable space and are installed within or onto an independent structural frame, e.g. detachable staircases and bathroom pods. Modular: Offsite preassembled volumetric components that form or assemble to form the actual structure, fabric and enclosing useable space of the construction. Units such as offices or classrooms can be fully constructed and finished internally offsite.
Non-Volumetric | From the information provided in the Tool, this project is suitable for the application of Offsite Construction. | The most appropriate application of offsite construction is non-volumetric prefabrication. | Non-volumetric: Offsite preassembly of components that have no usable space by themselves. These preassemblies may be structural or non-structural and include open and closed planar or panelised systems e.g., cladding panels, precast concrete sections: posts, beams, slabs and columns, and structural steelwork trusses. | Volumetric: Offsite preassembly of components that create usable space and are installed within or onto an independent structural frame, e.g. detachable staircases and bathroom pods. Modular: Offsite preassembled volumetric components that form or assemble to form the actual structure, fabric and enclosing useable space of the construction. Units such as offices or classrooms can be fully constructed and finished internally offsite.
Volumetric | From the information provided in the Tool, this project is suitable for the application of Offsite Construction. | The most appropriate application of offsite construction is volumetric prefabrication. | Volumetric: Offsite preassembly of components that create usable space and are installed within or onto an independent structural frame, e.g. detachable staircases and bathroom pods. | Non-volumetric: Offsite preassembly of components that have no usable space by themselves. These preassemblies may be structural or non-structural and include open and closed planar or panelised systems e.g., cladding panels, precast concrete sections: posts, beams, slabs and columns, and structural steelwork trusses. Modular: Offsite preassembled volumetric components that form or assemble to form the actual structure, fabric and enclosing useable space of the construction. Units such as offices or classrooms can be fully constructed and finished internally offsite.
Modular | From the information provided in the Tool, this project is suitable for the application of Offsite Construction. | The most appropriate application of offsite construction is modular prefabrication. | Modular: Offsite preassembled volumetric components that form or assemble to form the actual structure, fabric and useable space of the construction, often involving multiple specialised trades. Units such as offices or classrooms can be fully constructed and finished internally offsite. | Non-volumetric: Offsite preassembly of components that have no usable space by themselves. These preassemblies may be structural or non-structural and include open and closed planar or panelised systems e.g., cladding panels, precast concrete sections: posts, beams, slabs and columns, and structural steelwork trusses. Volumetric: Offsite preassembly of components that create usable space and are installed within or onto an independent structural frame, e.g. detachable staircases and bathroom pods.
Project Elements
Traditional | From the information provided, this element is not suited to Offsite Construction. | Traditional construction may be better suited to this element. Should OSC still be desired, additional time in design phase may be required.
Non-Volumetric | From the information provided, this element is suited to Offsite Construction. | The most appropriate application of offsite construction is non-volumetric prefabrication.
Volumetric | From the information provided, this element is suited to Offsite Construction. | The most appropriate application of offsite construction is volumetric prefabrication.
Modular | From the information provided, this element is suited to Offsite Construction. | The most appropriate application of offsite construction is modular prefabrication.

## Backend (hidden)
[13 empty] | 1 |  |  |  | 2 |  |  |  | 3
Question | Project Information | ANSWER | 1 | 2 | 3 | Influence Factor (1.0-3.0) | Additional Information | Modular | Volumetric | Non-Volumetric | Traditional |  | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional
1.1 | Is the project similar to others previously delivered? | 0 | Very similar | Some similar elements | It's new / unique | 3 | Repeated projects provide opportunity for savings in design reuse, component reuse and knowledge sharing | 0 | 0 | 0 | 0 |  | 10 | 8 | 8 | 2 | 8 | 8 | 8 | 5 | 2 | 4 | 4 | 8
1.2 | Is the project part of a larger program of works? | 0 | Yes | No |  | 3 | Programs of works across multiple sites provide opportunity for design reuse, bulk ordering of parts and program compression | 0 | 0 | 0 | 0 |  | 10 | 8 | 7 | 4 | 6 | 7 | 7 | 8 | 0 | 0 | 0 | 0
1.3 | Is there existing design and IP available for reuse? | 0 | Yes | No |  | 2 | - | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 4 | 2 | 4 | 4 | 8 | 0 | 0 | 0 | 0
1.4 | Is the project unique in terms of architectural design? | 0 | Architectural design is standardised | Some architectural design reuse | Completely unique (a landmark project) | 2 | Projects with uniquely designed architectural elements may be better suited to traditional construction methods | 0 | 0 | 0 | 0 |  | 8 | 7 | 7 | 3 | 4 | 4 | 6 | 6 | 2 | 4 | 7 | 9
1.5 | Does project handover need to happen urgently after initiation? | 0 | Yes | No |  | 1 | OSC allows for program fast-tracking through quicker construction time | 0 | 0 | 0 | 0 |  | 10 | 9 | 9 | 4 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0
1.6 | Does the project have requirements for increasing diversity? | 0 | Yes | No |  | 1 | The manufacturing environment of OSC has been shown to increase workforce diversity | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0
[7 empty] | Total | 0 | 0 | 0 | 0
[13 empty] | 1 |  |  |  | 2 |  |  |  | 3
Question | Project Factors |  | 1 | 2 | 3 | Influence Factor (1.0-3.0) Multipler | Additional Information | Modular | Volumetric | Non-Volumetric | Traditional |  | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional
2.1 | Is design repeatable or standardised? | 0 | Yes | No |  | 3 | Repeated or standardised design elements such as classrooms, bridge beams or housing modules. | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 4 | 2 | 4 | 4 | 8 | 0 | 0 | 0 | 0
2.2 | Is the project likely to require significant design changes during delivery? | 0 | Yes | No |  | 3 | OSC requires lock-in of design early in the project lifecycle | 0 | 0 | 0 | 0 |  | 2 | 2 | 4 | 10 | 9 | 8 | 8 | 8 | 0 | 0 | 0 | 0
2.3 | Is it important to reduce design complexity? | 0 | Yes | No |  | 2 | - | 0 | 0 | 0 | 0 |  | 8 | 6 | 5 | 4 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0
2.4 | Is it important to reduce site complexity? | 0 | Yes | No |  | 3 | OSC can reduce the number of trades onsite | 0 | 0 | 0 | 0 |  | 10 | 9 | 8 | 4 | 4 | 4 | 6 | 8 | 0 | 0 | 0 | 0
2.5 | Is construction constrained by external factors (e.g. occupation, school holidays)? | 0 | Very constrained | Some packages have constraints | No | 3 | Constraint on construction requires a tight turnaround onsite, reducing onsite complexity to meet program | 0 | 0 | 0 | 0 |  | 10 | 9 | 8 | 4 | 10 | 8 | 7 | 6 | 5 | 5 | 5 | 5
2.6 | Location remote from labour and infrastructure? | 0 | Remote | Regional | Urban | 3 | Geographically remote sites may not have access to multiple trades in a supply chain | 0 | 0 | 0 | 0 |  | 10 | 9 | 9 | 4 | 9 | 9 | 9 | 6 | 8 | 8 | 8 | 8
2.7 | Are site conditions uncertain? (e.g. geotechnical, contamination) | 0 | Yes | No |  | 1 | Sites with unknown existing conditions may require design changes to accommodate for contamination, subsurface utilities etc. | 0 | 0 | 0 | 0 |  | 4 | 6 | 6 | 8 | 6 | 6 | 6 | 8 | 0 | 0 | 0 | 0
2.8 | Is your project suseptible to construction delays due to weather? | 0 | Yes | No |  | 2 | Projects with susceptibility to delays due to weather may be better suited to manufacture of components offsite | 0 | 0 | 0 | 0 |  | 10 | 9 | 8 | 4 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
2.9 | Is there an appetite to take up innovation? | 0 | Innovation is a key metric | Not specifically, but interested | Not a key decision factor | 2 |  | 0 | 0 | 0 | 0 |  | 10 | 9 | 8 | 6 | 8 | 8 | 8 | 7 | 5 | 5 | 5 | 5
[7 empty] | Total | 0 | 0 | 0 | 0
[13 empty] | 1 |  |  |  | 2 |  |  |  | 3
Question | Construction Factors |  | 1 | 2 | 3 | Influence Factor (1.0-3.0) | Additional Information | Modular | Volumetric | Non-Volumetric | Traditional |  | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional
3.1 | How difficult is the access to the construction site for this element (e.g. transport, swept path area)? | 0 | Very difficult (e.g. route approval required) | Somewhat difficult (dimension considerations taken into account) | Not difficult (no considerations) | 2 | OSC can improve inventory management (just in time), decrease stage space requirements, and avoid double handling by allowing direct installation from the delivery vehicle. | 0 | 0 | 0 | 0 |  | 5 | 7 | 7 | 9 | 7 | 8 | 8 | 9 | 5 | 5 | 5 | 5
3.2 | How contained and/or constrained is the space/laydown area for the construction of this element? | 0 | Very constrained (no additional area) | Somewhat constrained (small area requiring additional scheduling for delivery) | No constraint (large laydown area adjacent to site) | 2 | Underground activities and small sites in dense urban environments usually have a contained/constrained space and limits offsite construction. | 0 | 0 | 0 | 0 |  | 1 | 2 | 4 | 9 | 7 | 8 | 8 | 9 | 8 | 6 | 6 | 5
3.3 | How significant are health & safety risks in the construction of this element? | 0 | Very important - project metric | Important | Not a key decision factor | 3 | Health and safety risks, such as falling from heights and working alongside live operations, can be drastically reduced by manufacturing offsite in a controlled environment where work can be automated and optimised. | 0 | 0 | 0 | 0 |  | 8 | 7 | 5 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
3.4 | How constrained are labour resources for this element? | 0 | Very constrained (tight labour market/highly skilled roles) | Somewhat constrained (schedule resources early) | No constraints | 2 | Labour resources may be constrained for roles that require high skills and experience. OSC allows people who are presently underrepresented in traditional construction to enter the workforce. | 0 | 0 | 0 | 0 |  | 10 | 9 | 8 | 6 | 8 | 8 | 8 | 7 | 5 | 5 | 5 | 5
3.5 | How important for the project is reduction of construction waste? | 0 | Very important - project metric | Important | Not a key decision factor | 3 | Environmental impacts are typically reduced as materials usage and movements are optimised. OSC typically increases energy efficiency and reduces waste by up to 40 per cent. | 0 | 0 | 0 | 0 |  | 8 | 7 | 5 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
3.6 | How important for the project is reduction of onsite traffic and distruption? | 0 | Very important - project metric | Important | Not a key decision factor | 3 | Fewer deliveries to the site of materials and components and an accelerated timeline with OSC mean less noise, disturbance, and pollution in the surrounding area. | 0 | 0 | 0 | 0 |  | 8 | 7 | 5 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
[7 empty] | Total | 0 | 0 | 0 | 0
[8 empty] | Modular | Volumetric | Non-Volumetric | Traditional
[7 empty] | Total | 0 | 0 | 0 | 0
Suitable Technology
[13 empty] | 1 |  |  |  | 2 |  |  |  | 3
Question | Element Design Factors |  | 1 | 2 | 3 | Influence Factor (1.0-3.0) | Additional Information | Modular | Volumetric | Non-Volumetric | Traditional |  | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional
4.1 | How complex is the design of this element? | 0 | Low complexity or standard design | Medium - design work required | High complexity, input required from multiple disciplines | 1 | Repeated projects provide opportunity for savings in design reuse, component reuse and knowledge sharing | 0 | 0 | 0 | 0 |  | 8 | 8 | 7 | 4 | 6 | 6 | 6 | 6 | 4 | 4 | 6 | 8
4.2 | How likely are significant design changes to occur during the construction phase of this element? | 0 | Unlikely - standard design | Possible | Very likely - designing from scratch | 3 | Programs of works across multiple sites provide opportunity for design reuse, bulk ordering of parts and program compression | 0 | 0 | 0 | 0 |  | 8 | 8 | 6 | 6 | 8 | 8 | 8 | 8 | 4 | 4 | 6 | 8
4.3 | How high is the level of design standardisation and/or repeatability of this element across the project/program? | 0 | Element repeated across project/program | Element somewhat repeated (e.g. in one package of works) | One-off | 2 | Repeated or standardised design elements such as road barriers, toilet blocks or standard-sized classrooms | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 4 | 4 | 6 | 6 | 4 | 0 | 3 | 5 | 8
4.4 | How easily can this element be reused for or from other projects via Digital Models, BIM or Digital Twins? | 0 | Project requirement to be uploaded to digital model or similar | It's possible but not required | Not a key decision factor | 2 | Projects with uniquely designed architectural elements may be better suited to traditional construction methods | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 6 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5
4.5 | How important is precision during construction to ensure high quality for this element? | 0 | Very important | Important | Not a key decision factor | 2 | Requirements for elevated levels of quality control or minimal defects, or specialised functionality such as earthquake, fire or blast resistant buildings lend the development more towards OSC. | 0 | 0 | 0 | 0 |  | 8 | 7 | 5 | 4 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5
[7 empty] | Total | 0 | 0 | 0 | 0 | Modular or volumetric construction have equal scores and are both suitable for this element
Question | Element Design Factors |  | 1 | 2 | 3 | Influence Factor (1.0-3.0) | Additional Information | Modular | Volumetric | Non-Volumetric | Traditional |  | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional
4.1 | How complex is the design of this element? | 0 | Low complexity or standard design | Medium - design work required | High complexity, input required from multiple disciplines | 1 |  | 0 | 0 | 0 | 0 |  | 8 | 8 | 7 | 4 | 6 | 6 | 6 | 6 | 4 | 4 | 6 | 8
4.2 | How likely are significant design changes to occur during the construction phase of this element? | 0 | Unlikely - standard design | Possible | Very likely - designing from scratch | 3 |  | 0 | 0 | 0 | 0 |  | 2 | 2 | 4 | 10 | 8 | 8 | 8 | 8 | 4 | 4 | 6 | 8
4.3 | How high is the level of design standardisation and/or repeatability of this element across the project/program? | 0 | Element repeated across project/program | Element somewhat repeated (e.g. in one package of works) | One-off | 2 |  | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 4 | 4 | 6 | 6 | 4 | 0 | 3 | 5 | 8
4.4 | How easily can this element be reused for or from other projects via Digital Models, BIM or Digital Twins? | 0 | Project requirement to be uploaded to digital model or similar | It's possible but not required | Not a key decision factor | 2 |  | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5
4.5 | How important is precision during construction to ensure high quality for this element? | 0 | Very important | Important | Not a key decision factor | 2 |  | 0 | 0 | 0 | 0 |  | 8 | 7 | 5 | 4 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5
[7 empty] | Total | 0 | 0 | 0 | 0 | Modular or volumetric construction have equal scores and are both suitable for this element
Question | Element Design Factors |  | 1 | 2 | 3 | Influence Factor (1.0-3.0) | Additional Information | Modular | Volumetric | Non-Volumetric | Traditional |  | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional | Modular | Volumetric | Non-Volumetric | Traditional
4.1 | How complex is the design of this element? | 0 | Low complexity or standard design | Medium - design work required | High complexity, input required from multiple disciplines | 1 |  | 0 | 0 | 0 | 0 |  | 8 | 8 | 7 | 4 | 6 | 6 | 6 | 6 | 4 | 4 | 6 | 8
4.2 | How likely are significant design changes to occur during the construction phase of this element? | 0 | Unlikely - standard design | Possible | Very likely - designing from scratch | 3 |  | 0 | 0 | 0 | 0 |  | 2 | 2 | 4 | 10 | 8 | 8 | 8 | 8 | 4 | 4 | 6 | 8
4.3 | How high is the level of design standardisation and/or repeatability of this element across the project/program? | 0 | Element repeated across project/program | Element somewhat repeated (e.g. in one package of works) | One-off | 2 |  | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 4 | 4 | 6 | 6 | 4 | 0 | 3 | 5 | 8
4.4 | How easily can this element be reused for or from other projects via Digital Models, BIM or Digital Twins? | 0 | Project requirement to be uploaded to digital model or similar | It's possible but not required | Not a key decision factor | 2 |  | 0 | 0 | 0 | 0 |  | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5
4.5 | How important is precision during construction to ensure high quality for this element? | 0 | Very important | Important | Not a key decision factor | 2 |  | 0 | 0 | 0 | 0 |  | 8 | 7 | 5 | 4 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5
[7 empty] | Total | 0 | 0 | 0 | 0 | Modular or volumetric construction have equal scores and are both suitable for this element
[8 empty] | Modular | Volumetric | Non-Volumetric | Traditional
[7 empty] | Total | 0 | 0 | 0 | 0