## Instructions
Instructions for use
The Responsible Entities Risk Consequence and Contingency (RERCC) Plan risk register template helps responsible entities comply with section 74F of the Circular Economy (Waste Reduction and Recycling) Act 2021 and regulation 12 of the Circular Economy (Waste Reduction and Recycling) (Risk, Consequence and Contingency Plans and Other Matters) Regulations 2023, by identifying, assessing, prioritising, and reporting enterprise risks.
This tool is structured as follows:
Lookup tab | The Lookup tab provides risk assessment criteria to allow users to assess identified risks using a scaled criteria table relevant to your business.
BEFORE YOU BEGIN
You will need to set up the scaled criteria table as shown in the example provided in Part 3: Risk Assessment of the RERCC Plan guidelines, that reflects the relevant criteria for each level of risk rating, relevant to your business.
Once established, update the risk matrix, consequence and likelihood lists in the lookup tab using the pre-prepared criteria.
Warning: this spreadsheet is packaged with risk rating criteria to illustrate how the spreadsheet and risk rating process operates. The prepackaged criteria may not be relevant to your business and could be misleading if not tailored to your business.
Risk Register tab | The risk register tab provides an editable risk register enabling documentation of risks, causes, consequences, controls and mitigations that supports risk review, monitoring and reporting
Disclaimer | The RERCC Plan risk register template may be of assistance to you, but the State of Victoria and its employees do not guarantee that the publication is without flaw of any kind or is wholly appropriate for your particular purposes and therefore disclaims all liability for any error, loss or other consequence which may arise from you relying on any information in this publication.
Risk management process
This template applies the risk management process set out in AS ISO31000:2018 Risk management guidelines as shown below.
Risk Register tab | The risk register tab contains a structure supporting the risk assessment, risk treatment, recording and monitoring stages of the process.
How to identify risks | Identify what can happen, where and when. Identify who or what is specifically involved in the source of the risk.
Consider what could go wrong that could impact the achievement of objectives or result in missed opportunities.
Identify why and how it can happen. Consider what might be the main causal factors of the event.
Consider short and long-term impacts and emerging, as well as current risks. Also, consider how quickly the risks are likely to materialise.
Consider where there are or may be dependencies and / or vulnerabilities.
Ensure all risks have an allocated a risk owner.
Use the columns under the 'Risk Identification' heading (columns A-H in the Risk Register tab) to populate the information about identified risks.
Links between CERCC and RERCC risks | The serious risks to widespread service continuity and in progressing and developing a more circular economy are described in the CERCC Plan (column I in the Risk Register). Responsible entities need to consider these risks, in conjunction with their own identified risks, and select related CERCC risks where relevant, to demonstrate due regard to the CERCC plan and shape their risk management interventions.
How to analyse risks | Consider the risks identified above, focusing on the causes and consequences.
What measures (controls) are currently in place to prevent the risk from arising, detect the risk if it does arise and reduce the severity of the consequences.
Use the columns under the 'Existing controls' heading (columns J-N in the Risk Register tab) to populate the controls currently in place to mitigate the identified risks.
Are the controls that are in place now to mitigate the risks working as expected? (control effectiveness).
Ensure all of the controls have a control owner.
How to rate risks | Given the controls that are currently in place, how do you rate the likelihood of the risk occurring and the level of consequence?
Use the columns under the 'Current risk assessment' heading (columns O-Q in the Risk Register tab) to document the rating for each risk.
Treatment plan | Review the Current risk ratings (column Q in the Risk Register tab). For each risk, determine if the risk rating is too high or at a level that you accept and select the corresponding risk treatment option.
Where risk ratings are considered too high despite existing controls, determine what more needs to be done to further reduce the risk.
Use the 'Treatment Plan' columns (columns R-V in the Risk Register tab) to document the additional measures that are required to further reduce the risk, ensuring they are funded, resourced and planned for.
Residual risk rating | What level of residual risk is anticipated to remain once the treatments have been completed?
Use the columns under 'Residual risk assessment' (columns W-Y in the Risk Register tab) to document the residual risk rating for each risk.
Monitoring | By using this risk register, you can monitor treatment progress and ensure that additional measures are implemented to reduce risk.
Reporting | Use of this risk register will assist you in meeting reporting requirements.
Reproduced by Department of Energy, Environment and Climate Action (DEECA) in Victoria with the permission of Standards Australia Limited under licence CFL0424DEECAVIC.
Copyright in AS ISO 31000:2018 vests in Standards Australia and ISO. Users must not copy or reuse this work without the permission of Standards Australia or the copyright owner.

## Risk Register
EXAMPLE Platypus Processing – RISK REGISTER
Risk Identification | [8 empty] | Existing Controls |  |  |  |  | CURRENT RISK ASSESSMENT |  |  | Treatment Plan |  |  |  |  | RESIDUAL RISK ASSESSMENT |  |  | Comments
[14 empty] | Likelihood | Consequence | [6 empty] | Likelihood | Consequence
Risk status | Risk ID | Date risk identified | Risk event | Cause | Consequence | Risk owner | Risk category | Relevant CERCC Plan risk | Controls | Control owner | Last control review date | Next control review date | Control effectiveness | Current likelihood rating | Level of consequence | Current risk rating | Risk treatment option | Treatment action details | Treatment owner | Treatment Due date | Treatment status | Residual likelihood rating | Level of consequence | Residual risk rating | Date risk last reviewed | Notes
Active | 1 | 2017-05-15 | EXAMPLE RISK : Cyber attack | Inadequate staff training | Operational shutdown | Joe Platypus | Information management and technology | External threats | Password management | Tina Leadbeater |  |  | Good | Almost certain | (-3) Moderate | High | Reduce the risk | Build and implement a regular penetration testing scheme to test effectivess of the control suite. | Sally Skink | 2024-12-31 | In progress | Possible | (-3) Moderate | Medium | 2023-12-15
Active | 1 | 2020-12-01 | EXAMPLE RISK : Cyber attack | Insufficient funding | Costs to restore systems | Joe Platypus | Information management and technology | External threats | Patching regime | Ned Bluetongue |  |  | Good | Almost certain | (-3) Moderate | High | Reduce the risk | Recurrent budget item for cyber attack | Ned Bluetongue | 2024-06-15 | In progress | Possible | (-3) Moderate | Medium | 2023-12-15
Active | 1 | 2021-07-21 | EXAMPLE RISK : Cyber attack | Inadequate internal cyber security capability | Operational shutdown | Joe Platypus | Information management and technology | External threats | Backup process | Sally Skink |  |  | Satisfactory | Almost certain | (-3) Moderate | High | Reduce the risk |  |  |  |  | Possible | (-3) Moderate | Medium | 2023-12-15
Active | 2 | 2021-07-01 | EXAMPLE RISK: EPA licence suspension | Failure to comply with licence conditions to manage air emissions | Loss of ability to process material. Waste stockpiling at upstream supply chains. Loss of down stream markets | Kate Wombat | Legal and compliance | Internal threats | Maintenance program reviewed and updated. Engagement program developed with upstream customers and down stream markets. | Amanda Apple |  |  | Satisfactory | Likely | (-3) Moderate | Significant | Reduce the risk | Staff capability assessment. | Amanda Apple | 2023-03-15 | Complete | Unlikely | (-2) Minor | Low | 2023-12-15

## Lookup
Lookup
Risk Matrix | Consequence | [6 empty] | Level of consequence | Likelihood | Control effectiveness | Risk category | Risk status | Risk treatment option | Action status | CERCC Risks
Likelihood |  |  | HARM (-) |  |  |  |  | (-1) Negligible | Rare | Good | Asset management and infrastructure | Active | Accept or retain the risk | Complete | Contamination
|  |  | -1 | -2 | -3 | -4 | -5 | (-2) Minor | Unlikely | Satisfactory | Business strategy development and delivery | Closed | Reduce the risk | Delayed | External threats
|  |  | (-1) Negligible Harm | (-2) Minor Harm | (-3) Moderate Harm | (-4) Major Harm | (-5) Extreme Harm | (-3) Moderate | Possible | Poor | Emergency management and business continuity |  | Share the risk | In progress | Planning
|  |  | Negligible | Minor | Moderate | Major | Extreme | (-4) Major | Likely | Uncontrolled | Financial management |  | Avoid the risk | Not started | Societal responses
| 5 | Almost certain | Medium | Significant | High | High | High | (-5) Extreme | Almost certain |  | Information management and technology |  |  |  | Internal threats
| 4 | Likely | Medium | Medium | Significant | High | High |  |  |  | Integrity |  |  |  | Economic stressors
| 3 | Possible | Low | Medium | Medium | Significant | High |  |  |  | Legal and compliance |  |  |  | No relevant CERCC risk identified
| 2 | Unlikely | Low | Low | Medium | Medium | Significant |  |  |  | Procurement and contract management
| 1 | Rare | Low | Low | Low | Medium | Significant |  |  |  | Project management
Public safety, liability and insurance
Resource management
Stakeholder Management
Workplace wellbeing and safety