## Sheet1
Project | Sector | Total estimated investment | Entity | Budget year | Estimated completion date | Project status | Estimated expenditure to 30.06.2025 | Estimated remaining expenditure | Notes
85 by 2025 (Level Crossing Removal) (metropolitan various) | Transport | $8,647M | Department of Transport and Planning | 2025-26 | qtr 2 2025-26 | Existing | $8,152M | $495M | The TEI has decreased by $99.400 million, comprising $88.500 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards, and a decrease of $10.900 million which has been reprioritised to Metro Tunnel (metropolitan various) initiative.
Additional acute mental health beds in regional Victoria (various) | Health and human services | $196M | Department of Health | 2025-26 | qtr 4 2028-29 | Existing | $20M | $176M
Albert Park Pit Building Redevelopment (Albert Park) | Culture, sport and community | tbc | Other PNFC | 2025-26 | qtr 3 2027-28 | Existing | tbc | tbc | This initiative was approved in the 2024-25 Budget. The TEI and estimated expenditure are not reported at this time as procurement arrangements are still to be finalised.
Arden Precinct Redevelopment (metropolitan) | Transport | tbc | Department of Transport and Planning | 2025-26 | tbc | Existing | tbc | tbc | The TEI and estimated completion date for this initiative cannot be disclosed at this time to protect commercial-in-confidence information.
Austin Hospital Emergency Department Upgrade (Heidelberg) | Health and human services | $275M | Department of Health | 2025-26 | qtr 2 2028-29 | Existing | $23M | $252M | This initiative is part of Labor's Financial Statement 2022.
Ballarat Health Services expansion and redevelopment and the new Central Energy Plant (Ballarat) | Health and human services | $650M | Department of Health | 2025-26 | qtr 2 2027-28 | Existing | $227M | $423M
Barwon Women's and Children's Hospital (Geelong) | Health and human services | $514M | Department of Health | 2025-26 | qtr 2 2029-30 | Existing | $67M | $447M | The TEI includes $50.000 million of Commonwealth Government funding under the Community Health and Hospitals Program agreement.
Best Start, Best Life: Infrastructure 2023-24 (statewide) | Education and training | $2,220M | Department of Education | 2025-26 | qtr 4 2030-31 | Existing | $187M | $2,033M | The TEI has decreased by $1.100 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The Pre-Prep element of Best Start, Best Life is a 15-year infrastructure program with an overall program completion date of 2036-37.
Better aged care services for regional Victorians (regional various) | Health and human services | $162M | Department of Health | 2025-26 | qtr 1 2028-29 | Existing | $17M | $145M | This initiative is part of Labor's Financial Statement 2022.
Big Housing Build (statewide) | Culture, sport and community | $2,247M | Homes Victoria | 2025-26 | qtr 4 2027-28 | Existing | $1,789M | $458M | The TEI has decreased by $79.157 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Building a better hospital for Melbourne's inner west (Footscray) | Health and human services | $1,999M | Department of Health | 2025-26 | qtr 2 2025-26 | Existing | $1,891M | $107M | The estimated completion date has been revised to quarter 2 2025-26 in line with a revised project schedule.
Building a world class hospital for Frankston families (Frankston) | Health and human services | $1,120M | Department of Health | 2025-26 | qtr 3 2027-28 | Existing | $918M | $202M | The estimated completion date has been revised to reflect the completion of main works by the end of 2025, with the remaining refurbishment and other works to be completed by quarter 3 2027-28.
Building a World Class Hospital in Maryborough (Maryborough) | Health and human services | $115M | Department of Health | 2025-26 | qtr 4 2025-26 | Existing | $101M | $14M
Building works stimulus (statewide) | Culture, sport and community | $177M | Homes Victoria | 2025-26 | qtr 2 2024-25 | Completed | $177M | $0M | The TEI has increased by $4.606 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
Car Parks for Commuters (statewide) | Transport | $610M | Victorian Rail Track | 2025-26 | qtr 2 2025-26 | Existing | $552M | $59M | The TEI has increased by $19.737 million due to additional Commonwealth Government funding for its remaining 50 per cent share of some joint projects. The TEI includes $141.740 million of Commonwealth Government funding.
Caulfield Rationalisation Works (metropolitan various) | Transport | $223M | Victorian Rail Track | 2025-26 | qtr 3 2025-26 | Completed | $215M | $0M | The TEI has decreased by $10.719 million due to $8.524 million reprioritisation of cost savings to the Metro Tunnel (metropolitan various) and $2.195 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Clyde Road Upgrade (metropolitan southeast) | Transport | $278M | Department of Transport and Planning | 2025-26 | qtr 1 2027-28 | Existing | $112M | $165M | The TEI has increased by $34.021 million due to additional Commonwealth Government funding associated with the Commonwealth Infrastructure Investment Program Strategic Review. The TEI is funded by $277.700 million of Commonwealth Government funding.
Community hospitals to give patients the best care (statewide) | Health and human services | $870M | Department of Health | 2025-26 | qtr 2 2026-27 | Existing | $632M | $238M | The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule.
Cooling our public housing towers (metropolitan) | Culture, sport and community | $101M | Homes Victoria | 2025-26 | qtr 4 2026-27 | Existing | $9M | $93M | The TEI has decreased by $25.700 million due to a reallocation to the Energy Efficiency in Social Housing initiative in line with a revised program scope. This initiative is part of Labor's Financial Statement 2022.
COVID catch-up plan (statewide) | Health and human services | $208M | Department of Health | 2025-26 | qtr 4 2028-29 | Existing | $132M | $75M
Dandenong Corridor Readiness Works (metropolitan various) | Transport | $257M | Victorian Rail Track | 2025-26 | qtr 2 2026-27 | Completed | $257M | $0M | The TEI has decreased by $18.476 million due to reprioritisation of cost savings to the Metro Tunnel (metropolitan various).
Delivering new police station infrastructure (statewide) | Justice and emergency services | $153M | Department of Justice and Community Services | 2025-26 | qtr 4 2027-28 | Existing | $88M | $65M | The TEI has increased by $89.987 million due to funding recognition for new police stations at Narre Warren, Clyde North and the new Wollert police station. The estimated completion date has been revised to quarter 4 2027-28 in line with the revised project schedule.
Delivering the Road Safety Action Plan (statewide) | Transport | $271M | Department of Transport and Planning | 2025-26 | qtr 4 2027-28 | Existing | $148M | $123M | The TEI has increased by $42.383 million due to additional Commonwealth Government funding, offset by a decrease of $1.563 million due to budgeted amounts being reclassified as operating instead of capital expenditure in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 due to the inclusion of an additional program of works. The TEI includes $184.887 million of Commonwealth Government funding.
Eastern Freeway Upgrade (Springvale to Hoddle) | Transport | $5,709M | Department of Transport and Planning | 2025-26 | qtr 2 2028-29 | Existing | tbc | tbc | The Commonwealth Government is contributing $5 billion to the North East Link program. The estimated expenditure will be reported as procurement processes and commercial arrangements are finalised.
E-Class Tram Infrastructure Program (metropolitan various) | Transport | $789M | Victorian Rail Track | 2025-26 | qtr 4 2027-28 | Existing | $599M | $190M
Emergency Departments Expansion Program – Casey Hospital and Werribee Mercy Hospital (Casey) (Werribee) | Health and human services | $280M | Department of Health | 2025-26 | qtr 4 2026-27 | Existing | $57M | $222M
Emergency Services High-priority infrastructure (statewide) | Justice and emergency services | $168M | Department of Justice and Community Services | 2025-26 | qtr 4 2026-27 | Existing | $121M | $46M | The TEI has increased by $40.110 million due to $17.002 million in funding being reprioritised from the Delivering Emergency Services Upgrades initiative for the VICSES Kilmore and VICSES Bannockburn and a further $23.108 million from Growth Areas Infrastructure Contributions program.
Essential maintenance and compliance 2022-23 (statewide) | Education and training | $119M | Department of Education | 2025-26 | qtr 4 2025-26 | Completed | $119M | $0M | The TEI has decreased by $1.447 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Expanding mental health treatment facilities for Victoria's youth (statewide) | Health and human services | $141M | Department of Health | 2025-26 | qtr 3 2025-26 | Existing | $81M | $60M | The estimated completion date has been revised to quarter 3 2025-26 due to land acquisition and planning approval delays.
Fishermans Bend Innovation Precinct at the former General Motors Holden Site – Stage 1 (Melbourne) | Transport | $198M | Department of Transport and Planning | 2025-26 | qtr 4 2025-26 | Existing | $194M | $4M | The TEI has increased by $18.300 million due to additional remediation work. The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule.
Forensic Mental Health Expansion Project Stage 1 and 2 (Fairfield) | Health and human services | $462M | Department of Health | 2025-26 | qtr 4 2025-26 | Existing | $390M | $72M | The main works will be completed by quarter 1 2025-26, with the estimated completion date revised to quarter 4 2025-26 due to decanting, refurbishment works and in line with a revised project schedule for the multi-deck car park.
FRV Capital Upgrades Program (statewide) | Justice and emergency services | $104M | Fire Rescue Victoria | 2025-26 | qtr 4 2027-28 | Existing | $47M | $57M | The TEI has decreased by $7.862 million due to a revised project scope.
Geelong City Deal (regional) | Culture, sport and community | $110M | Department of Jobs, Skills, Industry and Regions | 2025-26 | qtr 2 2026-27 | Existing | $30M | $79M | The TEI has decreased by $1.800 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 2 2026-27 in line with a revised schedule of works. The TEI includes $87.274 million of Commonwealth Government funding.
Great Ocean Road Renewal (Barwon South West) | Transport | $253M | Department of Transport and Planning | 2025-26 | qtr 1 2026-27 | Existing | $161M | $92M | The TEI has decreased by $2.431 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 1 2026-27 due to geotechnical works along the Inland Routes, and complexities with environmental approvals.
High Capacity Metro Trains (metropolitan various) | Transport | $2,262M | Victorian Rail Track | 2025-26 | qtr 2 2025-26 | Existing | $2,249M | $14M | The TEI has decreased by $2.520 million which has been reprioritised to East Pakenham Sub Station (Ryans Road) initiative. The estimated completion date has been revised to quarter 2 2025-26 due to the staging of complex signalling infrastructure works across major projects.
High-rise Redevelopment Program (metropolitan) | Culture, sport and community | $857M | Homes Victoria | 2025-26 | various | Existing | $181M | $676M | The project name has changed from ‘Public Housing Revitalisation Program’ when it was published in the 2024-25 Budget. The TEI has increased by $420.487 million due to the increased scope of works for redevelopment of towers at Malvern Road, South Yarra and Highett Street, Richmond as well as walk ups at the Richmond Estate announced in September 2024.
Homes Victoria Ground Lease Model Project 1 (metropolitan) | Culture, sport and community | $517M | Homes Victoria | 2025-26 | qtr 2 2026-27 | Existing | $457M | $60M | This project is being delivered as an availability PPP under a Ground Lease Model. The TEI includes project development, demolition, procurement costs, capital contribution, and construction costs being funded by Building Communities.
Homes Victoria Ground Lease Model Project 2 (metropolitan) | Culture, sport and community | $687M | Homes Victoria | 2025-26 | qtr 2 2026-27 | Existing | $503M | $184M | This project is being delivered as an availability PPP under a Ground Lease Model. The TEI includes project development, demolition, procurement costs, capital contribution, and construction costs being funded by Building Communities.
Horsham Renewable Energy Park | Energy | $364M | State Electricity Commission of Victoria | 2025-26 | qtr 2 2027-28 | New | $88M | $276M
Hospital Infrastructure Delivery Fund (statewide) – A new hospital for West Gippsland to put patients first – A new Queen Elizabeth II Hospital in Melbourne's East – Dandenong Hospital and Wonthaggi Hospital redevelopment | Health and human services | $103M | Department of Health | 2025-26 | qtr 2 2026-27 | Existing | $13M | $90M | The TEI has reduced by $12.990 million due to a revised project scope. This initiative is part of Labor’s Financial Statement 2022.
Housing Support Program - Priority Works (statewide) | Culture, sport and community | $101M | Homes Victoria | 2025-26 | qtr 4 2026-27 | New | $16M | $86M | The TEI is funded by $101.098 million of Commonwealth Government funding.
Ison Road Rail Overpass (Werribee) | Transport | $109M | Department of Transport and Planning | 2025-26 | qtr 2 2025-26 | Existing | $84M | $25M | The TEI has decreased by $1.914 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $56.900 million of Commonwealth Government funding.
Kananook Train Maintenance Facility Stage 2 (metropolitan) | Transport | $365M | Victorian Rail Track | 2025-26 | qtr 1 2025-26 | Existing | $292M | $73M | The TEI has decreased by $0.265 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Keeping Victorians moving (metropolitan) | Transport | $173M | Department of Transport and Planning | 2025-26 | qtr 4 2025-26 | Existing | $173M | $1M | The estimated completion date has been revised to quarter 4 2025-26 due to delays in the implementation of the final feature of the Situational Awareness platform.
Land acquisition (various) | Education and training | $237M | Department of Education | 2025-26 | qtr 1 2028-29 | New | $0M | $237M
Land Acquisition 2021-22 (various) | Education and training | $296M | Department of Education | 2025-26 | qtr 4 2026-27 | Existing | $214M | $82M | The TEI has decreased by $1.605 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 due to land acquisition timelines.
Land acquisition 2022-23 (various) | Education and training | $251M | Department of Education | 2025-26 | qtr 4 2025-26 | Existing | $224M | $27M | The TEI includes $16.700 million from the Growth Areas Infrastructure Contribution. The estimated completion date has been revised to quarter 4 2025-26 due to land acquisition timelines.
M80 Ring Road upgrade (metropolitan north and west) | Transport | $552M | Department of Transport and Planning | 2025-26 | qtr 2 2026-27 | Completed | $501M | $0M | The TEI has decreased by $90.630 million due to scope and timing for M80 Capacity Improvements - Princes Freeway to Western Freeway components. The TEI has decreased by $14.100 million due to budgeted amounts being reclassified as operating instead of capital, in line with accounting standards. The TEI includes $349.130 million of Commonwealth Government funding.
M80 Ring Road Upgrade (Greensborough) | Transport | $3,824M | Department of Transport and Planning | 2025-26 | qtr 2 2028-29 | Existing | $1,522M | $2,302M | The Commonwealth Government is contributing $5 billion to the North East Link program.
Maintaining Victoria's road network (statewide) | Transport | $146M | Department of Transport and Planning | 2025-26 | qtr 4 2025-26 | Existing | $139M | $7M | The TEI has decreased by $0.262 million due to budgeted amounts being reclassified as operating instead of capital expenditure in line with accounting standards. The estimated completion date has been revised to quarter 4 2025-26 due to finalisation of pavement rehabilitation, bridge and noise wall works.
Meeting ambulance response times (statewide) | Health and human services | $177M | Department of Health | 2025-26 | qtr 2 2026-27 | Existing | $158M | $19M | The estimated completion date has been revised to quarter 2 2026-27 due to delays in site acquisition and related approvals.
Melbourne Arts Precinct Transformation (Melbourne) | Culture, sport and community | $1,574M | Other PNFC | 2025-26 | qtr 2 2028-29 | Existing | $469M | $1,105M | The project name has changed from ‘Melbourne Arts Precinct Transformation Phase One (Melbourne)’ when it was published in the 2024-25 Budget.
Melton Line upgrade (statewide) | Transport | $641M | Victorian Rail Track | 2025-26 | qtr 4 2028-29 | Existing | $31M | $610M | The TEI includes $325.000 million of Commonwealth Government funding. This initiative is part of Labor’s Financial Statement 2022.
Men's prison system capacity (statewide) | Justice and emergency services | $809M | Department of Justice and Community Services | 2025-26 | qtr 4 2026-27 | Existing | $658M | $151M | The TEI has increased by $55.107 million due to funding being reprioritised from the Western Plains Correctional Centre and Women's Prison system capacity initiative. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Metro Tunnel (metropolitan various) | Transport | $13,480M | Victorian Rail Track | 2025-26 | qtr 2 2025-26 | Existing | $13,133M | $348M | The TEI has increased by $837.900 million, due to the additional payment of $745.000 million agreed between the State and Cross Yarra Partnership under the 2024 settlement agreement, State costs and the reprioritisation of savings from Dandenong Corridor Readiness Works (metropolitan various) ($18.476 million), Level Crossing Removal (metropolitan various) ($10.900 million) and Caulfield Reprioritisation Works ($8.524 million).
Metro Tunnel Readiness 2023-24 and 2024-25 (metropolitan) | Transport | $401M | Victorian Rail Track | 2025-26 | qtr 2 2025-26 | Existing | $253M | $148M | The TEI has increased by $8.514 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
Metropolitan Health Infrastructure Fund 2020-21 (metropolitan various) | Health and human services | $187M | Department of Health | 2025-26 | qtr 4 2026-27 | Existing | $150M | $37M | The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Metropolitan Road and Intersection Upgrades (metropolitan various) | Transport | $120M | Department of Transport and Planning | 2025-26 | qtr 3 2025-26 | Existing | $80M | $41M | The TEI has decreased by $1.003 million which has been reprioritised to Hurstbridge Line Upgrade Stage 2 (metropolitan various) initiative, which was listed as a completed project in the 2024-25 Budget.
Metropolitan train infrastructure renewal program (metropolitan various) | Transport | $575M | Victorian Rail Track | 2025-26 | qtr 4 2029-30 | Existing | $109M | $466M | The project name has changed from ‘Metropolitan rail infrastructure renewal program (metropolitan various)’ when it was published in the 2024-25 Budget. As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2024-25 to 2029-30.
Metropolitan tram infrastructure renewal program (metropolitan various) | Transport | $403M | Victorian Rail Track | 2025-26 | qtr 4 2029-30 | Existing | $67M | $336M | The project name has changed from ‘Metropolitan rail infrastructure renewal program (metropolitan various)’ when it was published in the 2024-25 Budget. As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2024-25 to 2029-30.
Mickleham Road Upgrade – Stage 1 (Greenvale) | Transport | $191M | Department of Transport and Planning | 2025-26 | qtr 2 2025-26 | Existing | $184M | $7M | The TEI has decreased by $15.950 million due to $12.790 million of savings and $3.159 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 2 2025-26 in line with a revised project schedule. The TEI includes $109.540 million of Commonwealth Government funding.
Modernisation of metropolitan Melbourne Public Sector Residential Aged Care Services Strategy: Stage 3 Kingston Project (Cheltenham) | Health and human services | $140M | Department of Health | 2025-26 | qtr 4 2025-26 | Completed | $88M | $0M
Modernise the Digital Train Radio System (metropolitan) | Transport | $180M | Victorian Rail Track | 2025-26 | qtr 2 2030-31 | Existing | $12M | $168M
Modular Classrooms Program (statewide) | Education and training | $148M | Department of Education | 2025-26 | qtr 4 2025-26 | New | $0M | $148M
Monash Medical Centre Redevelopment (Clayton) | Health and human services | $535M | Department of Health | 2025-26 | qtr 4 2028-29 | Existing | $14M | $521M | This initiative is part of Labor's Financial Statement 2022.
More help for Victorian mums and dads (statewide) | Health and human services | $125M | Department of Health | 2025-26 | qtr 2 2025-26 | Existing | $123M | $1M | The TEI has increased by $1.565 million due to market escalation.
More hospital and aged care beds for Melbourne’s East (Angliss Hospital Expansion Stage 2) (Upper Ferntree Gully) | Health and human services | $112M | Department of Health | 2025-26 | qtr 4 2026-27 | Existing | $38M | $74M
More VLocity trains 2022-23 (regional) | Transport | $229M | Victorian Rail Track | 2025-26 | qtr 1 2026-27 | Completed | $217M | $0M | The TEI has decreased by $21.375 million due to $6.375 million which has been reprioritised to East Pakenham Sub Station (Ryans Road) initiative and $15.000 million which has been reprioritised to Public Transport Ticketing Asset Renewal (statewide) initiative.
More VLocity trains 2023-24 (regional) | Transport | $571M | Victorian Rail Track | 2025-26 | qtr 4 2027-28 | Existing | $436M | $134M | The TEI has decreased by $30.000 million due to savings in completed stages of works which has been reprioritised to Public Transport Ticketing Asset Renewal (statewide) initiative. This initiative is part of Labor’s Financial Statement 2022.
Murray Basin Rail Project (regional various) | Transport | $840M | Victorian Rail Track | 2025-26 | qtr 1 2026-27 | Existing | $783M | $57M | The TEI has increased by $33.040 million due to $53.270 million of market escalation and complex signalling implementation, offset by a $20.230 million decrease relating to expenditure being reclassified as operating instead of capital in line with accounting standards. The estimated completion date has been revised to quarter 1 2026-27 in line with signalling works and the pipeline of projects schedule across the program. The TEI includes $528.116 million of Commonwealth Government funding.
National water infrastructure development fund - national partnership agreement (regional various) | Water | $116M | Department of Energy, Environment and Climate Action | 2025-26 | qtr 4 2024-25 | Completed | $116M | $0M | The TEI has decreased by $52.817 million due to the cessation of the funding agreement with the remaining funds being transferred to the National Water Grid Fund to expand the scope of the project. The estimated completion date has been revised to quarter 4 2024-25 in line with the revised delivery schedule. The TEI includes $116.076 million of Commonwealth Government funding.
New Melton Hospital (Cobblebank) | Health and human services | $1,488M | Department of Health | 2025-26 | qtr 1 2029-30 | Existing | $184M | $1,304M | The project agreement was signed on 29 October 2024. This project is a Public Private Partnership where the upfront capital investment has resulted in additional scope and whole-of-life benefits over the 25-year operating term while remaining within the project's affordability benchmark. The estimated completion date has been revised to quarter 1 2029-30 in line with the project schedule.
New metropolitan trains (statewide) | Transport | $986M | Victorian Rail Track | 2025-26 | qtr 3 2027-28 | Existing | $355M | $631M
New schools construction 2022-23 (statewide) | Education and training | $723M | Department of Education | 2025-26 | qtr 3 2025-26 | Completed | $722M | $0M | The TEI has increased by $0.033 million to extend scope for additional school requirements, funded by co-contributions from schools. The TEI includes a total of $0.670 million of co-contributions from schools.
New schools construction 2023-24 (statewide) | Education and training | $760M | Department of Education | 2025-26 | qtr 3 2026-27 | Existing | $430M | $330M | The TEI has increased by $88.609 million due to market escalation in the construction sector. The TEI includes $13.104 million reprioritised from the New schools construction 2024-25 program. The estimated completion date has been revised to quarter 3 2026-27 in line with a staged project schedule for some projects in the package. The 2025 opening schools included in this initiative opened at the start of 2025, and the 2026 opening schools included in this initiative are on track for a Day 1 Term 1 opening.
New schools construction 2024-25 (statewide) | Education and training | $935M | Department of Education | 2025-26 | qtr 2 2026-27 | Existing | $354M | $580M | The TEI has decreased by $13.104 million being reprioritised to the New schools construction 2023-24 program. The TEI includes $35.472 million from the Growth Areas Infrastructure Contribution. The estimated completion date has been revised to quarter 2 2026-27 in line with a staged project schedule for some projects in the package. The 2026 opening schools included in this initiative are on track for a Day 1 Term 1 opening.
New schools construction (metropolitan various) To open in 2027: - Aintree North Primary School (interim name) - Officer Brunt Road Specialist School (interim name) Additional stages of new schools: - Bemin Secondary College - Brinbeal Secondary College - Walcom Ngarrwa Secondary College - Yarrabing Secondary College Planning for new schools: - South Melbourne Primary School | Education and training | $336M | Department of Education | 2025-26 | qtr 3 2026-27 | New | $0M | $336M
New Tarneit railway station (Tarneit) | Transport | $163M | Victorian Rail Track | 2025-26 | qtr 3 2026-27 | Existing | $15M | $148M | The TEI has increased by $39.406 million due to market escalation, change in scope and station design to futureproof the station. The estimated completion date has been revised to quarter 3 2026-27 to reflect a revised forecast for practical completion obtained after contract award. The project remains on track for commencement of operations in 2026.
New trains for Sunbury (metropolitan various) | Transport | $1,735M | Victorian Rail Track | 2025-26 | qtr 2 2026-27 | Existing | $1,417M | $318M | The TEI has decreased by $27.243 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 2 2026-27 to reflect completion dates for residual works after Metro Tunnel completion.
New Wyndham Law Court Development (Werribee) | Justice and emergency services | $275M | Court Services Victoria | 2025-26 | qtr 4 2025-26 | Completed | $267M | $0M
Next Generation Trams (metropolitan various) | Transport | $1,440M | Victorian Rail Track | 2025-26 | qtr 4 2028-29 | Existing | $385M | $1,054M
North East Link – Primary Package (Tunnels) and State Tolling Corporation (Greensborough) | Transport | $14,034M | State Tolling Corporation | 2025-26 | qtr 2 2028-29 | Existing | $7,398M | $6,636M | The TEI includes the $11.100 billion contract with the Spark consortium to deliver the Primary Package and State and State Tolling Corporation costs associated with the delivery of the Primary Package. The Commonwealth Government is contributing $5.000 billion to the North East Link program. The TEI excludes financing costs associated with the Primary Package. The State Tolling Corporation is responsible for providing funding contributions to the North East Link – Primary Package (Tunnels) initiative.
North East Link Connections (Bulleen/Watsonia) | Transport | $2,642M | Department of Transport and Planning | 2025-26 | qtr 2 2028-29 | Existing | $1,263M | $1,379M | The Commonwealth Government is contributing $5 billion to the North East Link program.
Northern Hospital Redevelopment (Epping) | Health and human services | $813M | Department of Health | 2025-26 | qtr 2 2029-30 | Existing | $24M | $789M | This initiative is part of Labor’s Financial Statement 2022.
Nyaal Banyul Geelong Convention and Event Centre (Geelong) | Culture, sport and community | $449M | Department of Jobs, Skills, Industry and Regions | 2025-26 | qtr 4 2025-26 | Existing | $363M | $86M | The TEI includes $30.000 million of Commonwealth Government funding and $3.000 million of City of Greater Geelong funding. The estimated completion date of quarter 4 2025-26 reflects the completion of the convention and event centre. The TEI excludes financing, land acquisition and ongoing operating costs.
Pakenham Roads Upgrade (Pakenham) | Transport | $416M | Department of Transport and Planning | 2025-26 | qtr 3 2026-27 | Existing | $292M | $124M | The TEI has increased by $24.205 million due to additional Commonwealth Government funding associated with the Commonwealth Infrastructure Investment Program Strategic Review. The TEI is funded by $415.700 million of Commonwealth Government funding.
Parkville Precinct Redevelopment (Parkville) | Health and human services | $2,338M | Department of Health | 2025-26 | tbc | Existing | $122M | $2,216M | The project name has changed from ‘Redevelopment of Royal Melbourne Hospital and Royal Women's Hospital’ when it was published in the 2024-25 Budget.
Princes Highway Corridor (regional various) | Transport | $156M | Department of Transport and Planning | 2025-26 | qtr 2 2026-27 | Existing | $80M | $76M | The TEI includes $145.328 million of Commonwealth Government funding.
Public Housing Renewal Program (statewide) | Culture, sport and community | $286M | Homes Victoria | 2025-26 | qtr 3 2026-27 | Existing | $235M | $51M | The TEI has increased by $101.403 million to now include revenue from land sales and Homes Victoria funding. The scope has been revised to include additional social homes delivered at the Stokes/Penola site. The estimated completion date has been revised to quarter 3 2026-27 in line with the additional scope of works.
Public Transport Ticketing Asset Renewal (statewide) | Transport | $680M | Victorian Rail Track | 2025-26 | qtr 2 2028-29 | Existing | $208M | $472M | The TEI has increased by $136.735 million and includes savings identified from other rolling stock projects. The estimated completion date has been revised to quarter 2 2028-29 following a program reset and the finalisation of design requirements with delivery partners.
Ready for school: Kinder for every three-year-old 2019-20 (statewide) | Education and training | $278M | Department of Education | 2025-26 | qtr 4 2025-26 | Existing | $228M | $50M | The TEI has decreased by $4.357 million as a result of a TEI decrease of $5.693 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards, partially offset by a TEI increase of $1.336 million due to a revised project scope, funded by co-contributions from local councils. The TEI includes $0.576 million in co-contributions from schools and a total of $3.482 million in co-contributions from local councils.
Ready for school: kinder for every three-year-old 2023-24 (statewide) | Education and training | $208M | Department of Education | 2025-26 | qtr 3 2027-28 | Existing | $11M | $197M
Regional Health Infrastructure Fund (regional various) | Health and human services | $250M | Department of Health | 2025-26 | qtr 4 2026-27 | Existing | $242M | $8M | The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Regional Health Infrastructure Fund 2019-20 (regional various) | Health and human services | $100M | Department of Health | 2025-26 | qtr 4 2026-27 | Existing | $89M | $11M | The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Regional Health Infrastructure Fund 2020-21 (regional various) | Health and human services | $120M | Department of Health | 2025-26 | qtr 4 2026-27 | Existing | $94M | $26M | The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Regional Health Infrastructure Fund 2022-23 (regional various) | Health and human services | $300M | Department of Health | 2025-26 | qtr 4 2027-28 | Existing | $120M | $180M | The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule.
Regional Housing Fund (regional) | Culture, sport and community | $748M | Homes Victoria | 2025-26 | qtr 4 2027-28 | Existing | $124M | $624M | The TEI has increased by $47.301 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
Regional Rail Revival - Gippsland Line Upgrade Stage 1 (regional various) | Transport | $872M | Victorian Rail Track | 2025-26 | qtr 3 2025-26 | Existing | $830M | $43M | The TEI has increased by $309.520 million due to market escalation and complex signalling implementation. The estimated completion date has been revised to quarter 3 2025-26 in line with a revised project schedule. The TEI includes $737.848 million of Commonwealth Government funding.
Regional Rail Revival - Shepparton Line Upgrade - Stage 3 (Shepparton) | Transport | $408M | Victorian Rail Track | 2025-26 | tbc | Existing | $339M | $69M | The TEI has increased by $8.802 million due to $14.200 million increase as a result of market escalation and complex signalling implementation, offset by $5.398 million decrease relating to expenditure being reclassified as operating instead of capital in line with accounting standards. The estimated completion date is to be confirmed once the disruption schedule is finalised. The TEI includes $331.360 million of Commonwealth Government funding.
Regional Rail Revival - Warrnambool Line Upgrade - Stage 2 (regional various) | Transport | $266M | Victorian Rail Track | 2025-26 | qtr 4 2025-26 | Existing | $226M | $40M | The TEI has increased by $15.236 million due to $19.830 million increase as a result of market escalation and complex signalling implementation, offset by $4.594 million decrease relating to expenditure being reclassified as operating instead of capital in line with accounting standards. The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule. The TEI includes $224.856 million of Commonwealth Government funding.
Regional Rail Revival - Waurn Ponds Track Duplication - Stage 2 (regional various) | Transport | $900M | Victorian Rail Track | 2025-26 | qtr 3 2026-27 | Completed | $868M | $0M | The TEI has increased by $73.300 million due to market escalation and complex signalling implementation. The TEI includes $788.099 million of Commonwealth Government funding.
Regional rail sustainability 2021-22 (statewide) | Transport | $465M | Victorian Rail Track | 2025-26 | qtr 2 2025-26 | Existing | $452M | $12M | The estimated completion date has been revised to quarter 2 2025-26 to allow for the procurement of materials.
Regional rail sustainability 2022-23 (statewide) | Transport | $205M | Victorian Rail Track | 2025-26 | qtr 4 2025-26 | Existing | $166M | $39M
Regional rail sustainability (statewide) | Transport | $149M | Victorian Rail Track | 2025-26 | qtr 4 2026-27 | New | $0M | $149M
Regional road upgrades 2022-23 (regional) | Transport | $101M | Department of Transport and Planning | 2025-26 | qtr 4 2027-28 | Existing | $22M | $79M | The TEI has increased by $9.500 million due to $9.600 million additional Commonwealth Government funding, offset by a decrease of $0.100 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. The TEI includes $38.798 million of Commonwealth Government funding.
Relocatable Buildings Program 2024-25 (statewide) | Education and training | $160M | Department of Education | 2025-26 | qtr 2 2025-26 | Existing | $154M | $6M | The TEI has increased by $7.425 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 2 2025-26 in line with a revised project schedule.
Road Blitz (statewide) | Transport | $1,200M | Department of Transport and Planning | 2025-26 | tbc | New | $0M | tbc | The TEI includes $1.000 billion of Commonwealth Government funding. The estimated cash flows and completion date will be disclosed following further project development activities.
Road Blitz to Get Families Home Sooner and Safer (statewide) | Transport | $768M | Department of Transport and Planning | 2025-26 | qtr 4 2028-29 | Existing | $81M | $687M | The TEI has increased by $93.750 million due to $108.182 million additional Commonwealth Government funding and a $5.479 million increase due to additional third-party contributions, offset by an $18.000 million decrease following further scoping of the program and a decrease of $1.911 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $357.577 million of Commonwealth Government funding. This initiative is part of Labor’s Financial Statement 2022.
Road maintenance 2024-25 (statewide) | Transport | $105M | Department of Transport and Planning | 2025-26 | qtr 4 2025-26 | Existing | $84M | $21M | The project name has changed from ‘Road maintenance (statewide)’ when it was published in the 2024-25 Budget. The estimated completion date has been revised to quarter 4 2025-26 to undertake final seals on delivered rehabilitation projects.
Road Maintenance and Renewal (statewide) | Transport | $1,091M | Department of Transport and Planning | 2025-26 | qtr 4 2032-33 | Existing | $85M | $1,006M
Road Safety Action Plan 2 (statewide) | Transport | $239M | Department of Transport and Planning | 2025-26 | qtr 4 2028-29 | New | $2M | $237M | The TEI includes $45.088 million of Commonwealth Government funding and $193.905 million of funding from the Transport Accident Commission.
Road Safety Strategy (statewide) | Transport | $277M | Department of Transport and Planning | 2025-26 | qtr 4 2025-26 | Completed | $194M | $0M | The TEI includes $183.300 million of Commonwealth Government funding. The TEI also includes funding from the Transport Accident Commission.
Rolling stock maintenance and disposal programs (statewide) | Transport | $108M | Victorian Rail Track | 2025-26 | qtr 1 2025-26 | Existing | $82M | $26M | The TEI has decreased by $9.768 million which has been reprioritised to East Pakenham Sub Station (Ryans Road) initiative.
Rural and Regional PSRACS Revitalisation Strategy Stage 1 (2022-23) (regional various) | Health and human services | $143M | Department of Health | 2025-26 | qtr 4 2027-28 | Existing | $74M | $69M
Social Housing Accelerator Program (statewide) | Culture, sport and community | $480M | Homes Victoria | 2025-26 | qtr 4 2027-28 | Existing | $104M | $376M | The TEI has increased by $16.665 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
South Dynon Train Maintenance Facility Stage 2 (statewide) | Transport | $297M | Victorian Rail Track | 2025-26 | qtr 1 2026-27 | Existing | $197M | $100M
Special school upgrades 2022-23 (statewide) | Education and training | $331M | Department of Education | 2025-26 | qtr 2 2026-27 | Existing | $280M | $52M | The TEI has increased by $4.905 million to extend scope for additional school requirements, funded by co-contributions from schools. The TEI includes a total of $5.355 million of co-contributions from schools. The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule.
State Basketball Centre redevelopment (Knox) | Culture, sport and community | $129M | Other PNFC | 2025-26 | qtr 1 2025-26 | Completed | $129M | $0M | The TEI includes a $27.000 million contribution from the Knox City Council.
Suburban Parks Program (Creating a Ring of New Parkland) (metropolitan) | Environment | $212M | Department of Energy, Environment and Climate Action | 2025-26 | qtr 4 2024-25 | Completed | $212M | $212M | The TEI has increased by $1.726 million to reflect revised project costings. The project was previously published in the 2024-25 Budget as Completed. However, the estimated completion date has been revised to quarter 4 2025-26 to reflect timing of land acquisitions.
Melbourne Airport Rail (metropolitan various) | Transport | tbc | Victorian Rail Track | 2025-26 | tbc | Existing | $933M | tbc | The State and Commonwealth governments have committed $5.000 billion each to the project. In March 2025, a Memorandum of Understanding was agreed between the State, Commonwealth and Australia Pacific Airports (Melbourne), committing all parties to work towards recommencing the project and develop a path to construction. The TEI, future estimated cash flows, and the estimated completion date for the project will be disclosed once project details are finalised. In March 2025, the State and Commonwealth governments jointly committed to deliver the Sunshine Station Superhub as a first step towards a rail line to Melbourne Airport and a future electrified Melton Line. To progress Sunshine Station Superhub the Commonwealth has committed an additional $2 billion and the State Government has brought forward $2 billion.
Suburban Rail Loop East – Main Works (metropolitan various) | Transport | tbc | Victorian Rail Track | 2025-26 | tbc | Existing | tbc | tbc | The Suburban Rail Loop East is expected to cost between $30.000 billion – $34.500 billion and is targeting delivery by 2035. The expected cost includes $3.610 billion (GST exclusive) for the Tunnels South contract from Cheltenham to Glen Waverley, and $1.710 billion (GST exclusive) for the Tunnels North contract between Glen Waverley and Box Hill. Contract award for the Linewide package to build the fleet of high-tech SRL trains and the signalling system, and to operate and maintain the SRL East network is expected in 2025. The TEI, estimated expenditure and estimated completion date will be disclosed following the procurement of the remaining main works packages. The TEI includes $2.200 billion of Commonwealth Government funding for land acquisition and early works.
Suburban Rail Loop East – Development, Initial and Early Works (metropolitan various) | Transport | $2,372M | Victorian Rail Track | 2025-26 | qtr 3 2025-26 | Existing | $1,820M | $551M
Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade (statewide) | Transport | $3,318M | Department of Transport and Planning | 2025-26 | qtr 4 2028-29 | Existing | $2,620M | $699M | The TEI has increased by $795.487 million including the addition of the Yan Yean Road Upgrade – Stage 2 initiative. The estimated completion date has been revised to quarter 4 2028-29 in line with a revised project schedule. The TEI includes $1 577.369 million of Commonwealth Government funding.
Sunshine Station Masterplan (Sunshine) | Transport | tbc | Victorian Rail Track | 2025-26 | tbc | Existing | tbc | tbc | The TEI, estimated expenditure and estimated completion date of the Sunshine Station Masterplan will be disclosed as part of further development of the Sunshine Station Superhub procurement process.
Sunshine Station Superhub (metropolitan various) | Transport | $4,140M | Victorian Rail Track | 2025-26 | qtr 2 2030-31 | New | $0M | $4,140M | The TEI includes $2.000 billion of Commonwealth Government funding.
Sustaining statewide health service delivery at The Alfred (Prahran) | Health and human services | $118M | Department of Health | 2025-26 | qtr 2 2029-30 | Existing | $0M | $118M | The estimated completion date has been revised to quarter 2 2029-30 to accommodate the need to stage work around clinical service requirements.
Targeted Road Safety Works (statewide) | Transport | $123M | Department of Transport and Planning | 2025-26 | qtr 2 2026-27 | Existing | $82M | $41M | The TEI has increased by $16.971 million as a result of project cost increases. The completion date has been revised to quarter 2 2026-27 to align with the current schedule of works. The TEI includes $85.295 million of Commonwealth Government funding.
Technology and resources to support Victoria’s fines system (statewide) | Justice and emergency services | $180M | Department of Justice and Community Services | 2025-26 | qtr 4 2025-26 | Existing | $161M | $19M
The Alfred Hospital urgent infrastructure (Prahran) | Health and human services | $175M | Department of Health | 2025-26 | qtr 4 2029-30 | Existing | $15M | $160M
Train radio system upgrade (metropolitan) | Transport | $190M | Victorian Rail Track | 2025-26 | qtr 4 2027-28 | Existing | $75M | $116M | The TEI has decreased by $15.000 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Tram infrastructure upgrades (metropolitan various) | Transport | $421M | Victorian Rail Track | 2025-26 | qtr 1 2025-26 | Existing | $384M | $38M | The TEI has decreased by $6.996 million due to $6.600 million being reprioritised to the Preparing the Network for Next Generation Trams (metropolitan various) initiative and $0.396 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Twenty five more level crossing removals by 2030 (Level Crossing Removal) (metropolitan various) | Transport | $6,449M | Department of Transport and Planning | 2025-26 | qtr 4 2029-30 | Existing | $924M | $5,525M | The TEI has decreased by $60.723 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Warrnambool Base Hospital redevelopment (incl Warrnambool Logistics Hub) (Warrnambool) | Health and human services | $396M | Department of Health | 2025-26 | qtr 4 2026-27 | Existing | $100M | $296M | The TEI has increased by $11.900 million due to market escalation.
Werribee Main Road Interchange Upgrade (Werribee) | Transport | $250M | Department of Transport and Planning | 2025-26 | tbc | New | $0M | $250M | The TEI includes $125.000 million of Commonwealth Government funding. The estimated completion date will be disclosed following further project development activities.
West Gate Tunnel (metropolitan various) | Transport | $10,159M | Department of Transport and Planning | 2025-26 | qtr 2 2025-26 | Existing | $9,556M | $603M
Western Highway duplication - Ballarat to Stawell (regional various) | Transport | $656M | Department of Transport and Planning | 2025-26 | tbc | Existing | $610M | $46M | The estimated completion date is to be confirmed once planning activities are completed. The TEI includes $499.380 million of Commonwealth Government funding.