## Sheet1
Project | Sector | Total estimated investment | Entity | Budget year | Estimated completion date | Project status | Estimated expenditure to 30.06.2025 | Estimated remaining expenditure | Notes
85 by 2025 (Level Crossing Removal) (metropolitan various) | Transport | $8592M | Department of Transport and Planning | 2026-27 | qtr 4 2027-28 | Completed | $8314M | $0M | The TEI has decreased by $55.735 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Additional acute mental health beds in regional Victoria (various) | Health and human services | $196M | Department of Health | 2026-27 | qtr 4 2028-29 | Existing | $27M | $136M
Albion station upgrade (Albion) | Transport | tbc | Victorian Rail Track | 2026-27 | tbc | Existing | $7M | tbc | The TEI, estimated expenditure and estimated completion date will be disclosed when the procurement process is finalised.
Arden Precinct Redevelopment (metropolitan) | Transport | tbc | Department of Transport and Planning | 2026-27 | tbc | Existing | tbc | tbc | The TEI and estimated completion date for this initiative cannot be disclosed at this time to protect commercial-in-confidence information.
Austin Hospital Emergency Department Upgrade (Heidelberg) | Health and human services | $275M | Department of Health | 2026-27 | qtr 2 2028-29 | Existing | $76M | $116M | This initiative is part of Labor’s Financial Statement 2022.
Ballarat Health Services expansion and redevelopment and the new Central Energy Plant (Ballarat) | Health and human services | $650M | Department of Health | 2026-27 | qtr 2 2027-28 | Existing | $438M | $73M
Barwon Women's and Children's Hospital (Geelong) | Health and human services | $514M | Department of Health | 2026-27 | qtr 2 2028-29 | Existing | $210M | $150M | The estimated completion date has been revised to quarter 2 2028-29 in line with a revised project schedule. The TEI includes $50.000 million of Commonwealth Government funding under the Community Health and Hospitals Program agreement.
Best Start, Best Life: Infrastructure 2023-24 (statewide) | Education and training | $1943M | Department of Education | 2026-27 | qtr 4 2030-31 | Existing | $485M | $1101M | The TEI has decreased by $276.901 million due to $300.000 million being reprioritised to the Best Start, Best Life: Infrastructure 2026-27 initiative and $1.001 million being reclassified as operating instead of capital expenditure, in line with accounting standards, partially offset by $24.100 million Commonwealth Government funding from the Building Early Education Fund (BEEF). The Pre-Prep element of Best Start, Best Life is a 15-year infrastructure program with an overall program completion date of 2036-37.
Best Start, Best Life: Infrastructure 2026-27 (statewide) | Education and training | $305M | Department of Education | 2026-27 | qtr 4 2030-31 | New | $0M | $292M | The TEI includes $300.000 million reallocated from the Best Start, Best Life: Infrastructure initiative funded in the 2023-24 Budget.
Better aged care services for regional Victorians (regional various) | Health and human services | $162M | Department of Health | 2026-27 | qtr 1 2028-29 | Existing | $46M | $32M | This initiative is part of Labor’s Financial Statement 2022.
Big Housing Build (statewide) | Culture, sport and community | $2227M | Homes Victoria | 2026-27 | qtr 4 2027-28 | Existing | $1821M | $19M | The TEI has decreased by $20.000 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with the accounting standards.
Building a better hospital for Melbourne's inner west (Footscray) | Health and human services | $1999M | Department of Health | 2026-27 | qtr 2 2026-27 | Completed | $1996M | $0M
Building a world class hospital for Frankston families (Frankston) | Health and human services | $1120M | Department of Health | 2026-27 | qtr 3 2027-28 | Existing | $1056M | $22M
Building a World Class Hospital in Maryborough (Maryborough) | Health and human services | $115M | Department of Health | 2026-27 | qtr 4 2026-27 | Completed | $111M | $0M
Car Parks for Commuters (statewide) | Transport | $610M | Victorian Rail Track | 2026-27 | qtr 2 2027-28 | Completed | $563M | $0M | The TEI includes $141.740 million of Commonwealth Government funding.
CFA Capital Upgrades Program (statewide) | Justice and emergency services | $109M | Department of Justice and Community Safety | 2026-27 | qtr 4 2028-29 | Existing | $76M | $17M | The TEI has increased by $27.663 million, $9.500 million due to funds being reprioritised from the Delivering Emergency Services Upgrades (statewide) initiative, $17.663 million reprioritised from the Building more Country Fire Authority stations (regional) initiative, and $0.500 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2028-29 in line with a revised project schedule.
Clyde Road Upgrade (metropolitan southeast) | Transport | $278M | Department of Transport and Planning | 2026-27 | qtr 4 2026-27 | Existing | $194M | $23M | The estimated completion date has been revised to quarter 4 2026-27 in line with favourable weather conditions for construction at critical stages. The TEI is funded by $277.700 million of Commonwealth Government funding.
Communities and families information technology transformation program (statewide) | Health and human services | $106M | Department of Families, Fairness and Housing | 2026-27 | qtr 4 2028-29 | New | $0M | $92M
Community hospitals to give patients the best care (statewide) | Health and human services | $870M | Department of Health | 2026-27 | qtr 4 2026-27 | Existing | $752M | $1M | The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Cooling our public housing towers (metropolitan) | Culture, sport and community | $101M | Homes Victoria | 2026-27 | qtr 4 2026-27 | Existing | $29M | $0M | This initiative is part of Labor’s Financial Statement 2022.
COVID catch-up plan (statewide) | Health and human services | $122M | Department of Health | 2026-27 | qtr 4 2026-27 | Existing | $120M | $0M | The TEI has decreased by $85.939 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 in line with the removal of non-capitalised components.
Dandenong Hospital Redevelopment (Dandenong) | Health and human services | $305M | Department of Health | 2026-27 | qtr 4 2031-32 | New | $0M | $291M | The TEI includes $86.872 million provided in the 2023-24 Budget in the Hospital Infrastructure Delivery Fund (statewide) initiative.
Delburn Wind Farm (Delburn) | Energy | $789M | State Electricity Commission of Victoria | 2026-27 | qtr 2 2028-29 | New | $129M | $149M
Delivering new Country Fire Authority fleet (statewide) | Justice and emergency services | $100M | Department of Justice and Community Safety | 2026-27 | qtr 4 2035-36 | New | $0M | $90M
Delivering new police station infrastructure (statewide) | Justice and emergency services | $150M | Department of Justice and Community Safety | 2026-27 | qtr 3 2027-28 | Existing | $114M | $13M | The TEI has decreased by $3.000 million due to funds being reprioritised to the Critical police station infrastructure (Melbourne) initiative. The estimated completion date has been revised to quarter 3 2027-28 in line with a revised project schedule.
Delivering the Road Safety Action Plan (statewide) | Transport | $271M | Department of Transport and Planning | 2026-27 | qtr 4 2027-28 | Existing | $159M | $55M | The TEI has decreased by $0.125 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $184.887 million of Commonwealth Government funding.
Eastern Freeway Upgrade (Springvale to Hoddle) | Transport | $5709M | Department of Transport and Planning | 2026-27 | qtr 2 2028-29 | Existing | $2935M | $1080M | The estimated expenditure has now been disclosed following contract award. The Commonwealth Government is contributing $5.000 billion to the North East Link program.
E-Class Tram Infrastructure Program (metropolitan various) | Transport | $789M | Victorian Rail Track | 2026-27 | qtr 4 2027-28 | Existing | $656M | $33M
Emergency Departments Expansion Program – Casey Hospital and Werribee Mercy Hospital (Casey) (Werribee) | Health and human services | $280M | Department of Health | 2026-27 | qtr 4 2026-27 | Existing | $152M | $0M
Emergency Services High-priority infrastructure (statewide) | Justice and emergency services | $182M | Department of Justice and Community Safety | 2026-27 | qtr 4 2027-28 | Existing | $126M | $33M | The TEI has increased by $13.861 million, with $13.261 million due to funds being reprioritised from the Delivering a new Victoria State Emergency Service Footscray unit (Maidstone) initiative, $0.100 million reprioritised from the Delivering Emergency Services Upgrades (statewide) initiative, and $0.500 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 in line with the revised delivery program.
Expanding mental health treatment facilities for Victoria's youth (statewide) | Health and human services | $141M | Department of Health | 2026-27 | qtr 4 2026-27 | Completed | $110M | $0M
Fishermans Bend Innovation Precinct at the former General Motors Holden Site – Stage 1 (Melbourne) | Transport | $198M | Department of Transport and Planning | 2026-27 | qtr 2 2026-27 | Existing | $184M | $5M | The estimated completion date has been revised to quarter 2 2026-27 in line with delays arising from external utilities authorities.
Forensic Mental Health Expansion Project Stage 1 and 2 (Fairfield) | Health and human services | $462M | Department of Health | 2026-27 | qtr 4 2026-27 | Existing | $430M | $3M | The estimated completion date has been revised to quarter 4 2026-27 in line with complex decanting activities associated with refurbishment works and completion of required town planning approvals.
FRV Capital Upgrades Program (statewide) (b) | Justice and emergency services | $104M | Department of Justice and Community Safety | 2026-27 | qtr 4 2027-28 | Existing | $53M | $37M
Great Ocean Road Renewal (Barwon South West) | Transport | $253M | Department of Transport and Planning | 2026-27 | qtr 4 2027-28 | Existing | $196M | $12M | The estimated completion date has been revised to quarter 4 2027-28 in line with further development on Beauty Gully Road, Maits Rest Safety Improvements and landslip works.
High Capacity Metro Trains (metropolitan various) | Transport | $2262M | Victorian Rail Track | 2026-27 | qtr 4 2025-26 | Completed | $2262M | $0M
High-rise Redevelopment Program (metropolitan) | Culture, sport and community | $1201M | Homes Victoria | 2026-27 | various | Existing | $277M | $606M | The TEI has increased by $344.011 million, comprising an increase of $329.718 million for the expanded scope of works for the redevelopment of seven towers across six sites in Albert Park, Flemington, Kensington, North Melbourne, Prahran and St Kilda, and a further increase of $20.986 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards, partially offset by $6.692 million reprioritised to the Public Housing Renewal Program initiative.
Homes Victoria Ground Lease Model Project 1 (metropolitan) | Culture, sport and community | $517M | Homes Victoria | 2026-27 | qtr 2 2026-27 | Existing | $511M | $0M
Homes Victoria Ground Lease Model Project 2 (metropolitan) | Culture, sport and community | $687M | Homes Victoria | 2026-27 | qtr 2 2026-27 | Existing | $603M | $0M
Horsham Renewable Energy Park (Horsham) | Energy | $364M | State Electricity Commission of Victoria | 2026-27 | qtr 2 2027-28 | Existing | $231M | $41M
Ison Road Rail Overpass (Werribee) | Transport | $109M | Department of Transport and Planning | 2026-27 | qtr 4 2026-27 | Completed | $87M | $0M | The TEI has increased by $0.119 million due to additional Commonwealth Government funding. The TEI includes $57.019 million of Commonwealth Government funding.
Kananook Train Maintenance Facility Stage 2 (metropolitan) | Transport | $365M | Victorian Rail Track | 2026-27 | qtr 1 2027-28 | Completed | $292M | $0M | The TEI has increased by $0.117 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
Keeping Victorians moving (metropolitan) | Transport | $173M | Department of Transport and Planning | 2026-27 | qtr 4 2025-26 | Completed | $173M | $0M
Land acquisition (various) | Education and training | $104M | Department of Education | 2026-27 | qtr 4 2028-29 | New | $0M | $43M | The TEI includes $1.880 million reprioritised from the Land acquisition (2025-26) initiative. The TEI includes $10.000 million from the Growth Areas Infrastructure Contribution.
Land Acquisition 2021-22 (various) | Education and training | $290M | Department of Education | 2026-27 | qtr 4 2027-28 | Existing | $224M | $19M | The TEI has decreased by $5.495 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 due to land acquisition timelines.
Land acquisition 2022-23 (various) | Education and training | $251M | Department of Education | 2026-27 | qtr 4 2027-28 | Existing | $238M | $12M | The TEI has decreased by $0.085 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 due to land acquisition timelines. The TEI includes $16.700 million from the Growth Areas Infrastructure Contribution.
Land acquisition 2025-26 (various) | Education and training | $235M | Department of Education | 2026-27 | qtr 1 2028-29 | Existing | $60M | $19M | The TEI has decreased by $1.880 million due to a reprioritisation to the Land acquisition 2026-27 initiative.
M80 Ring Road Upgrade (Greensborough) | Transport | $3824M | Department of Transport and Planning | 2026-27 | qtr 2 2028-29 | Existing | $2387M | $652M | The Commonwealth Government is contributing $5.000 billion to the North East Link program.
Maintaining Victoria's road network (statewide) | Transport | $145M | Department of Transport and Planning | 2026-27 | qtr 4 2026-27 | Existing | $142M | $0M | The TEI has decreased by $0.392 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 due to finalisation of pavement rehabilitation works.
Meeting ambulance response times (statewide) | Health and human services | $177M | Department of Health | 2026-27 | qtr 4 2027-28 | Existing | $163M | $0M | The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule.
Melbourne Airport Rail (metropolitan various) | Transport | tbc | Victorian Rail Track | 2026-27 | tbc | Existing | $941M | tbc | The State and Commonwealth governments have committed $5.000 billion each to the project. In March 2025, a Memorandum of Understanding was agreed between the State, Commonwealth and Australia Pacific Airports (Melbourne), committing all parties to developing an approach to deliver the project. The TEI, future estimated cash flows, and the estimated completion date for the project will be disclosed once project details are finalised. In March 2025, the State and Commonwealth governments jointly committed to deliver the Sunshine Station Superhub as the first stage of a rail line to Melbourne Airport and a future electrified Melton Line. To progress Sunshine Station Superhub the Commonwealth has committed an additional $2.000 billion and the State Government has brought forward $2.000 billion.
Melbourne Arts Precinct Transformation (Melbourne) | Culture, sport and community | $1671M | Other PNFC | 2026-27 | qtr 2 2028-29 | Existing | $785M | $500M | The TEI has increased by $96.617 million due to a $95.000 million Commonwealth Government contribution to the project and $1.617 million being reclassified as capital instead of operating expenditure, in line with accounting standards.
Melbourne Indoor Sports Centre (Albert Park) | Culture, sport and community | $426M | Other PNFC | 2026-27 | qtr 1 2028-29 | Existing | $189M | $67M | The project name has changed from the ‘Albert Park Pit Building Redevelopment’ when it was published in the 2025-26 Budget. The TEI and estimated expenditure are now disclosed following the finalisation of the procurement process, and include the costs for site remediation. The new Melbourne Indoor Sports Centre is planned to be ready for the community and to host the Formula 1 Australian Grand Prix in 2028. The estimated completion date has been revised to quarter 1 2028-29 to reflect the final works relating to all year-round building use.
Melton Line upgrade (statewide) | Transport | $601M | Victorian Rail Track | 2026-27 | qtr 2 2027-28 | Existing | $138M | $280M | The TEI has decreased by $40.409 million which has been reprioritised to the Next steps for future Melton Line electrification (metropolitan) initiative. The estimated completion date has been revised to quarter 2 2027-28 in line with a revised forecast for practical completion obtained after contract award. The TEI includes $325.000 million of Commonwealth Government funding. This initiative is part of Labor’s Financial Statement 2022.
Men's prison system capacity (statewide) | Justice and emergency services | $809M | Department of Justice and Community Safety | 2026-27 | qtr 4 2026-27 | Existing | $691M | $5M
Metro Tunnel (metropolitan various) | Transport | $13480M | Victorian Rail Track | 2026-27 | qtr 2 2028-29 | Completed | $13380M | $0M | Major construction of the Metro Tunnel is now complete.
Metro Tunnel Readiness (metropolitan) | Transport | $415M | Victorian Rail Track | 2026-27 | qtr 2 2027-28 | Existing | $373M | $2M | The TEI has increased by $14.100 million due to funding previously published separately for the 'Switching on the Metro Tunnel' initiative. The estimated completion date has been revised to quarter 2 2027-28 in line with complex electrical works for the North Melbourne electrical intake substation project.
Metropolitan Health Infrastructure Fund 2020-21 (metropolitan various) | Health and human services | $187M | Department of Health | 2026-27 | qtr 4 2027-28 | Existing | $157M | $0M | The estimated completion date has been revised to quarter 4 2027-28 to accommodate delivery of a recently funded additional project.
Metropolitan Road and Intersection Upgrades (metropolitan various) | Transport | $120M | Department of Transport and Planning | 2026-27 | qtr 3 2026-27 | Existing | $95M | $5M | The estimated completion date has been revised to quarter 3 2026-27 to reflect safety improvements for the South Gippsland Highway and Lynbrook Boulevard projects.
Metropolitan road upgrades 2022-23 (metropolitan various) | Transport | $103M | Department of Transport and Planning | 2026-27 | qtr 3 2027-28 | Existing | $60M | $6M | The TEI has increased by $4.212 million due to additional developer contributions. The estimated completion date has been revised to quarter 3 2027-28 in line with approved scope and scheduling for the Derrimut Road and Boundary Intersection Upgrade project.
Metropolitan train infrastructure renewal program (metropolitan various) | Transport | $549M | Victorian Rail Track | 2026-27 | qtr 4 2030-31 | Existing | $113M | $325M | As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for metropolitan train infrastructure renewals from 2025-26 to 2030-31.
Metropolitan tram infrastructure renewal program (metropolitan various) | Transport | $407M | Victorian Rail Track | 2026-27 | qtr 4 2030-31 | Existing | $97M | $253M | As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for tram infrastructure renewals from 2025-26 to 2030-31.
Mickleham Road Upgrade – Stage 1 (Greenvale) | Transport | $192M | Department of Transport and Planning | 2026-27 | qtr 2 2026-27 | Completed | $190M | $0M | The TEI has increased by $1.444 million due to an increase of $1.500 million, reprioritised from existing funds. This increase is partially offset by a $0.056 million decrease due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $109.540 million of Commonwealth Government funding.
Modernise the Digital Train Radio System (metropolitan) | Transport | $180M | Victorian Rail Track | 2026-27 | qtr 2 2030-31 | Existing | $30M | $122M
Modular Classrooms Program (statewide) | Education and training | $174M | Department of Education | 2026-27 | qtr 4 2026-27 | New | $0M | $0M
Modular Classrooms Program 2025-26 (statewide) | Education and training | $148M | Department of Education | 2026-27 | qtr 4 2026-27 | Completed | $148M | $0M | The TEI has increased by $0.043 million to extend the scope for additional school requirements, funded by a co-contribution from a school.
Monash Medical Centre Redevelopment (Clayton) | Health and human services | $535M | Department of Health | 2026-27 | qtr 4 2028-29 | Existing | $50M | $344M | This initiative is part of Labor's Financial Statement 2022.
More help for Victorian mums and dads (statewide) | Health and human services | $125M | Department of Health | 2026-27 | qtr 2 2026-27 | Completed | $125M | $0M
More hospital and aged care beds for Melbourne’s East (Angliss Hospital Expansion Stage 2) (Upper Ferntree Gully) | Health and human services | $112M | Department of Health | 2026-27 | qtr 4 2026-27 | Existing | $98M | $0M
More new trains (metropolitan) | Transport | $674M | Victorian Rail Track | 2026-27 | qtr 2 2030-31 | New | $0M | $599M | The TEI includes reprioritisation of $146.000 million from the New metropolitan trains (statewide) initiative.
More VLocity trains 2023-24 (regional) | Transport | $571M | Victorian Rail Track | 2026-27 | qtr 4 2027-28 | Existing | $531M | $20M
Murray Basin Rail Project (regional various) | Transport | $840M | Victorian Rail Track | 2026-27 | qtr 1 2026-27 | Existing | $814M | $14M | The TEI has decreased by $0.289 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $528.116 million of Commonwealth Government funding.
National water grid fund (statewide) | Water | $190M | Department of Energy, Environment and Climate Action | 2026-27 | qtr 4 2028-29 | Existing | $113M | $41M
New Melton Hospital (Cobblebank) | Health and human services | $1488M | Department of Health | 2026-27 | qtr 1 2029-30 | Existing | $314M | $848M
New metropolitan trains (statewide) | Transport | $840M | Victorian Rail Track | 2026-27 | qtr 3 2027-28 | Existing | $375M | $326M | The TEI has decreased by $146.000 million which has been reprioritised to the More new trains (metropolitan) initiative.
New schools construction (statewide) To open in 2028: - Rockbank Toolern Road Primary School (Interim Name) - Thompsons East Primary School (Interim Name) - Wollahra Secondary School (Interim Name) New campus construction to open in 2029: - South Melbourne Primary School Additional stages of new schools: - Homestead Senior Secondary College - Wulerrp Secondary College - Yubup Primary School Planning and early works: - Arden Secondary School (Interim Name) - Pattersons Road Secondary School (Interim Name) - Preston High School (New Campus) | Education and training | $392M | Department of Education | 2026-27 | qtr 1 2029-30 | New | $0M | $214M | The TEI includes $107.652 million from the Growth Areas Infrastructure Contribution.
New schools construction 2023-24 (statewide) | Education and training | $756M | Department of Education | 2026-27 | qtr 3 2026-27 | Existing | $631M | $1M | The TEI has decreased by $4.505 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The 2025 opening schools included in this initiative opened at the start of 2025, and the 2026 opening schools included in this initiative opened at the start of 2026.
New schools construction 2024-25 (statewide) | Education and training | $929M | Department of Education | 2026-27 | qtr 2 2026-27 | Existing | $797M | $1M | The TEI has decreased by $5.853 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $35.472 million from the Growth Areas Infrastructure Contribution. The 2026 opening schools included in this initiative opened at the start of 2026.
New schools construction 2025-26 (statewide) | Education and training | $336M | Department of Education | 2026-27 | qtr 3 2026-27 | Existing | $127M | $4M
New Tarneit railway station (Tarneit) | Transport | $163M | Victorian Rail Track | 2026-27 | qtr 3 2026-27 | Existing | $109M | $11M
New trains for Sunbury (metropolitan various) | Transport | $1735M | Victorian Rail Track | 2026-27 | qtr 2 2026-27 | Existing | $1557M | $0M
Next Generation Trams (metropolitan various) | Transport | $1436M | Victorian Rail Track | 2026-27 | qtr 4 2028-29 | Existing | $427M | $828M | The TEI has decreased by $3.367 million due to reprioritisation of savings to the Tram infrastructure upgrades (metropolitan various) initiative.
North East Link – Primary Package (Tunnels) and State Tolling Corporation (Greensborough) | Transport | $14034M | State Tolling Corporation | 2026-27 | qtr 2 2028-29 | Existing | $9998M | $1383M | The TEI includes the $11.100 billion contract with the Spark consortium to deliver the Primary Package as well as State and State Tolling Corporation costs associated with the delivery of the Primary Package. The Commonwealth Government is contributing $5.000 billion to the North East Link program. The TEI excludes financing costs associated with the Primary Package. The State Tolling Corporation is responsible for providing funding contributions to the ‘North East Link – Primary Package (Tunnels)’ initiative.
North East Link Connections (Bulleen/Watsonia) | Transport | $2642M | Department of Transport and Planning | 2026-27 | qtr 2 2028-29 | Existing | $1855M | $306M | The Commonwealth Government is contributing $5.000 billion to the North East Link program.
Northern Hospital Redevelopment (Epping) | Health and human services | $813M | Department of Health | 2026-27 | qtr 2 2029-30 | Existing | $127M | $571M | This initiative is part of Labor’s Financial Statement 2022.
Nyaal Banyul Geelong Convention and Event Centre (Geelong) | Culture, sport and community | $449M | Department of Jobs, Skills, Industry and Regions | 2026-27 | qtr 4 2025-26 | Completed | $449M | $0M | The TEI includes $30.000 million of Commonwealth Government funding and $3.000 million of City of Greater Geelong funding. The TEI excludes financing, land acquisition and ongoing operating costs.
Pakenham Roads Upgrade (Pakenham) | Transport | $416M | Department of Transport and Planning | 2026-27 | qtr 1 2026-27 | Existing | $368M | $2M | The TEI has increased by $0.621 million due to additional developer contributions. The estimated completion date has been revised to quarter 1 2026-27 in line with accelerated progress. The TEI includes $415.700 million of Commonwealth Government funding.
Parkville Precinct Redevelopment (Parkville) | Health and human services | $2338M | Department of Health | 2026-27 | tbc | Existing | $185M | $1983M
Preparing the network for Next Generation Trams (metropolitan various) | Transport | $167M | Victorian Rail Track | 2026-27 | qtr 4 2027-28 | Existing | $37M | $15M | The TEI has increased by $98.056 million and the completion date has been revised to quarter 4 2027-28 to incorporate funding previously published separately for the Preparing the network for Next Generation Trams initiative announced in the 2025-26 Budget.
Princes Highway Corridor (regional various) | Transport | $156M | Department of Transport and Planning | 2026-27 | qtr 4 2026-27 | Existing | $104M | $7M | The estimated completion date has been revised to quarter 4 2026-27 due to interdependencies with the relocation of the existing rail level crossing. The TEI includes $145.328 million of Commonwealth Government funding.
Public Housing Renewal Program (statewide) | Culture, sport and community | $293M | Homes Victoria | 2026-27 | qtr 1 2027-28 | Existing | $257M | $0M | The TEI has increased by $6.692 million due to funding being reprioritised from the High-rise Redevelopment Program initiative to facilitate modifications at Stokes Penola, North Melbourne and Northcote to support relocations. The estimated completion date has been revised to quarter 1 2027-28 in line with a revised project schedule.
Public Transport Ticketing Asset Renewal (statewide) | Transport | $680M | Victorian Rail Track | 2026-27 | qtr 2 2028-29 | Existing | $331M | $269M
Ready for school: Kinder for every three-year-old 2019-20 (statewide) | Education and training | $273M | Department of Education | 2026-27 | qtr 4 2026-27 | Existing | $241M | $0M | The TEI has decreased by $4.645 million due to $4.651 million being reclassified as operating instead of capital expenditure, in line with accounting standards, partially offset by a TEI increase of $0.006 million due to a revised project scope, funded by co-contributions from local councils. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. The TEI includes $0.576 million in co-contributions from schools and a total of $3.488 million in co-contributions from local councils.
Ready for school: kinder for every three-year-old 2023-24 (statewide) | Education and training | $208M | Department of Education | 2026-27 | qtr 3 2027-28 | Existing | $64M | $10M | The TEI has decreased by $0.027 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Regional Health Infrastructure Fund (regional various) | Health and human services | $250M | Department of Health | 2026-27 | qtr 4 2026-27 | Existing | $241M | $0M
Regional Health Infrastructure Fund 2019-20 (regional various) | Health and human services | $100M | Department of Health | 2026-27 | qtr 4 2026-27 | Existing | $93M | $0M
Regional Health Infrastructure Fund 2020-21 (regional various) | Health and human services | $120M | Department of Health | 2026-27 | qtr 4 2026-27 | Existing | $106M | $0M
Regional Health Infrastructure Fund 2022-23 (regional various) | Health and human services | $300M | Department of Health | 2026-27 | qtr 4 2027-28 | Existing | $142M | $127M
Regional Housing Fund (regional) | Culture, sport and community | $748M | Homes Victoria | 2026-27 | qtr 4 2027-28 | Existing | $252M | $79M
Regional rail freight infrastructure maintenance (statewide) | Transport | $103M | Victorian Rail Track | 2026-27 | qtr 4 2027-28 | New | $0M | $11M
Regional Rail Revival - Gippsland Line Upgrade Stage 1 (regional various) | Transport | $862M | Victorian Rail Track | 2026-27 | qtr 3 2027-28 | Completed | $861M | $0M | The TEI has decreased by $9.710 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $732.698 million of Commonwealth Government funding.
Regional Rail Revival - Shepparton Line Upgrade - Stage 3 (Shepparton) | Transport | $403M | Victorian Rail Track | 2026-27 | qtr 4 2027-28 | Completed | $369M | $0M | The TEI has decreased by $5.408 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $331.360 million of Commonwealth Government funding.
Regional Rail Revival - Warrnambool Line Upgrade - Stage 2 (regional various) | Transport | $265M | Victorian Rail Track | 2026-27 | qtr 4 2027-28 | Completed | $235M | $0M | The TEI has decreased by $0.740 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $224.376 million of Commonwealth Government funding.
Regional rail sustainability (regional) | Transport | $181M | Victorian Rail Track | 2026-27 | qtr 4 2029-30 | New | $0M | $41M | The TEI includes reprioritisation of $26.098 million from the Regional rail sustainability 2025-26 initiative.
Regional rail sustainability 2021-22 (statewide) | Transport | $437M | Victorian Rail Track | 2026-27 | qtr 4 2025-26 | Completed | $437M | $0M | The TEI has decreased by $27.800 million due to V/Line delivering its regional rail freight maintenance program below the original allocations.
Regional rail sustainability 2022-23 (statewide) | Transport | $188M | Victorian Rail Track | 2026-27 | qtr 4 2026-27 | Existing | $183M | $0M | The TEI has decreased by $17.036 million due to V/Line delivering its regional rail freight maintenance program below the original allocation. The estimated completion date has been revised to quarter 4 2026-27 in line with the close-out of procurement and legacy system upgrades.
Regional rail sustainability 2025-26 (statewide) | Transport | $123M | Victorian Rail Track | 2026-27 | qtr 4 2026-27 | Existing | $95M | $0M | The TEI has decreased by $26.098 million which has been reprioritised to the new Regional Rail Sustainability (regional) initiative.
Regional road upgrades 2022-23 (regional) | Transport | $101M | Department of Transport and Planning | 2026-27 | qtr 4 2027-28 | Existing | $34M | $49M | The TEI has decreased by $0.500 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $38.798 million of Commonwealth Government funding.
Relocatable Buildings Program 2024-25 (statewide) | Education and training | $160M | Department of Education | 2026-27 | qtr 4 2026-27 | Existing | $160M | $0M | The TEI has increased by $0.588 million to extend the scope for additional school requirements, funded by a co-contribution from the school. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Road Blitz (statewide) | Transport | $1210M | Department of Transport and Planning | 2026-27 | tbc | Existing | $71M | $1039M | The TEI has increased by $10.389 million due to additional developer contributions of $11.866 million, partially offset by a $1.477 million decrease due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $1.000 billion of Commonwealth Government funding. The estimated expenditure for the program is now disclosed following project development activities. The estimated completion date will be disclosed following further project development activities.
Road Blitz to Get Families Home Sooner and Safer (statewide) | Transport | $766M | Department of Transport and Planning | 2026-27 | qtr 4 2028-29 | Existing | $297M | $197M | The TEI has decreased by $1.138 million due to $6.390 million being reclassified as operating instead of capital expenditure, in line with accounting standards. This decrease is partially offset by an increase of $1.277 million from additional third-party contributions and $3.918 million reprioritised from the Safer and Better Connected Communities. The TEI includes $361.008 million of Commonwealth Government funding. This initiative is part of Labor’s Financial Statement 2022.
Road maintenance (statewide) | Transport | $133M | Department of Transport and Planning | 2026-27 | qtr 4 2026-27 | New | $0M | $0M
Road maintenance 2024-25 (statewide) | Transport | $105M | Department of Transport and Planning | 2026-27 | qtr 4 2026-27 | Existing | $98M | $0M | The estimated completion date has been revised to quarter 4 2026-27 due to finalisation of pavement rehabilitation works.
Road Maintenance and Renewal (statewide) | Transport | $1081M | Department of Transport and Planning | 2026-27 | qtr 4 2032-33 | Existing | $160M | $850M | The TEI has decreased by $10.300 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Road Safety Action Plan 2 - Infrastructure Program (statewide) | Transport | $141M | Department of Transport and Planning | 2026-27 | qtr 4 2027-28 | Existing | $0M | $105M | This initiative has been separated into two projects. The TEI has decreased by $13.276 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $140.541 million of funding from the Transport Accident Commission.
Rolling stock maintenance and disposal programs (statewide) | Transport | $108M | Victorian Rail Track | 2026-27 | qtr 3 2027-28 | Existing | $89M | $9M | The estimated completion date has been revised to quarter 3 2027-28 due to a temporary project pause during the transition from MR4 to MR5 tram franchisee period.
Rural and Regional PSRACS Revitalisation Strategy Stage 1 2022-23 (regional various) | Health and human services | $143M | Department of Health | 2026-27 | qtr 4 2027-28 | Existing | $123M | $3M
Social Housing Accelerator Program (statewide) | Culture, sport and community | $480M | Homes Victoria | 2026-27 | qtr 4 2027-28 | Existing | $267M | $43M
South Dynon Train Maintenance Facility Stage 2 (statewide) | Transport | $297M | Victorian Rail Track | 2026-27 | qtr 1 2026-27 | Existing | $254M | $27M
Special school upgrades 2022-23 (statewide) | Education and training | $333M | Department of Education | 2026-27 | qtr 4 2027-28 | Existing | $315M | $6M | The TEI has increased by $1.651 million to extend the scope for additional school requirements, funded by co-contributions from schools. The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. The TEI includes a total of $7.006 million of co-contributions from schools.
Suburban parks program (creating a ring of new parkland) (metropolitan) | Environment | $212M | Department of Energy, Environment and Climate Action | 2026-27 | qtr 4 2026-27 | Existing | $212M | $0M | The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule to reflect timing of land acquisitions.
Suburban Rail Loop East – Development, Initial and Early Works (metropolitan various) | Transport | $2327M | Victorian Rail Track | 2026-27 | qtr 4 2030-31 | Completed | $2099M | $0M | The TEI has decreased by $44.800 million which has been reprioritised to the Suburban Rail Loop East – Main Works (metropolitan various) initiative for the Westernport-Altona-Geelong pipeline scope of works. Delivery of Suburban Rail Loop Initial and Early Works is now complete. The financial completion date aligns with the finalisation of costs for land acquired to support project delivery.
Suburban Rail Loop East – Main Works (metropolitan various) | Transport | tbc | Victorian Rail Track | 2026-27 | qtr 2 2035-36 | Existing | $4584M | tbc | The Suburban Rail Loop East is expected to cost between $30.000 billion – $34.500 billion and is targeting delivery by 2035. The expected cost includes $3.610 billion (GST exclusive) for the Tunnels South contract from Cheltenham to Glen Waverley, $1.710 billion (GST exclusive) for the Tunnels North contract between Glen Waverley and Box Hill, and $6.745 billion (GST exclusive) for Linewide delivery phase activities. Contract award for the Stations works packages is expected by 2027. The TEI and remaining expenditure will be disclosed following the procurement of the remaining main works packages. The TEI includes $2.200 billion of Commonwealth Government funding for land acquisition and early works and the Commonwealth Government has committed to additional funding as part of the Federal Budget in May 2026.
Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade (statewide) | Transport | $3321M | Department of Transport and Planning | 2026-27 | qtr 4 2028-29 | Existing | $2773M | $301M | The TEI has increased by $2.405 million due to additional developer contributions of $2.643 million and $0.088 million in Commonwealth Government funding, partially offset by a $0.326 million decrease due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $1 577.369 million of Commonwealth Government funding.
Sunshine Station Masterplan (Sunshine) | Transport | tbc | Victorian Rail Track | 2026-27 | tbc | Existing | tbc | tbc | The TEI, estimated expenditure and estimated completion date of the Sunshine Station Masterplan will be disclosed as part of further development of the Sunshine Station Superhub procurement process.
Sunshine Station Superhub (metropolitan various) | Transport | $4140M | Victorian Rail Track | 2026-27 | qtr 2 2030-31 | Existing | $170M | $3240M | The TEI includes $2.000 billion of Commonwealth Government funding.
Sustaining statewide health service delivery at The Alfred (Prahran) | Health and human services | $118M | Department of Health | 2026-27 | qtr 2 2029-30 | Existing | $4M | $55M
Targeted Road Safety Works (statewide) | Transport | $122M | Department of Transport and Planning | 2026-27 | qtr 4 2026-27 | Existing | $81M | $17M | The TEI has decreased by $0.337 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 in line with approved scope and scheduling for the Western Highway Realignment at Pykes Creek project. The TEI includes $85.295 million of Commonwealth Government funding.
Technology and resources to support Victoria’s fines system (statewide) | Justice and emergency services | $190M | Department of Justice and Community Safety | 2026-27 | qtr 4 2026-27 | Existing | $185M | $0M | The TEI has increased by $10.000 million reflecting increased delivery complexity. The completion date has been revised to quarter 4 2026–27 in line with a revised program schedule.
The Alfred Hospital urgent infrastructure (Prahran) | Health and human services | $175M | Department of Health | 2026-27 | qtr 4 2029-30 | Existing | $31M | $109M
Train radio system upgrade (metropolitan) | Transport | $190M | Victorian Rail Track | 2026-27 | qtr 4 2027-28 | Existing | $88M | $12M
Tram infrastructure upgrades (metropolitan various) | Transport | $425M | Victorian Rail Track | 2026-27 | qtr 1 2027-28 | Completed | $398M | $0M | The TEI has increased by $3.218 million due to $3.367 million of additional scope including an expanded solar system and inclusion of a gatehouse and tram crossover at the Maidstone Tram Maintenance facility, offset by a decrease of $0.149 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Twenty-five more level crossing removals (Level Crossing Removal) (metropolitan various) | Transport | $6411M | Department of Transport and Planning | 2026-27 | qtr 4 2031-32 | Existing | $1702M | $3727M | The TEI has decreased by $38.238 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2031-32 to align Highett Road and Wickham Road, Highett and Latrobe Street, Mentone level crossing removals with the Suburban Rail Loop delivery schedule to realise construction efficiencies and minimise disruption for Frankston line passengers.
Urban Congestion Fund (statewide) | Transport | $152M | Department of Transport and Planning | 2026-27 | tbc | Existing | $84M | $52M | The estimated completion date is to be confirmed following approval of the scope by the Commonwealth Government. The TEI is funded by $152.182 million of Commonwealth Government funding.
Victorian Renewable Energy Terminal (metropolitan) | Transport | $124M | Department of Transport and Planning | 2026-27 | tbc | New | $34M | $11M | The estimated completion date is pending environmental approval processes. The TEI includes $7.328 million from Port of Hastings Corporation.
Warrnambool Base Hospital redevelopment (incl Warrnambool Logistics Hub) (Warrnambool) | Health and human services | $396M | Department of Health | 2026-27 | qtr 3 2027-28 | Existing | $157M | $105M | The estimated completion date has been revised to quarter 3 2027-28 in line with a revised project schedule.
Werribee Main Road Interchange Upgrade (Werribee) | Transport | $190M | Department of Transport and Planning | 2026-27 | qtr 1 2029-30 | Existing | $23M | $121M | The TEI has decreased by $59.933 million due to an updated project business case. The estimated completion date is now disclosed following the completion of project development activities. The TEI includes $95.033 million of Commonwealth Government funding.
West Gate Tunnel (metropolitan various) | Transport | $10159M | Department of Transport and Planning | 2026-27 | qtr 2 2027-28 | Completed | $10000M | $0M
Western Highway duplication - Ballarat to Stawell (regional various) | Transport | tbc | Department of Transport and Planning | 2026-27 | tbc | Existing | $617M | $57M | The TEI has been revised to ‘tbc’ and is to be confirmed following further project development and engagement with the Commonwealth Government. The estimated completion date will be confirmed following further project development. The TEI includes $499.380 million of Commonwealth Government funding.